## Document Control
Document Control
Document Template Number | SCB Cocteau - Change - 0001
Change Number
Change Title | Datastore Restoration for VM - hklvdpapp071
Change Short Description | Datastore Restoration for VM - hklvdpapp071
Security Classification | For internal use
Version | 1.7.1
Status | Initial
Source | Atos
Document Date
Author(s) | Mahesh Sonwane
Planned Data Reviewed Date
Planned Data Reviewer (s)
Actual Data Reviewed Date
Actual Data Reviewer (s)
Contents |  | (press "+"-sign to show hidden rows)
Sheet | Description
Document Control | Information pertaining to document control (this sheet)
Atos CRQ Impl Plan | Atos Change Request Implementation & Backout Plan
Target Readers for completed file |  | (press "+"-sign to show hidden rows)
Reader Group | Distribution Method
Respective Atos Tower / SMC
SDMs
List of Changes |  | (press "+"-sign to show hidden rows)
Version | Summar of Version Change | Date | Author(s)
0.1 | Initial Template | 01 Mar 2019 | Chris Harvey / Leon Lim
1.0 | Initial Release for general use | 2019-03-22 | Chris Harvey / Leon Lim
1.1 | Added "Postponed@Cancelled" & "Unsuccessful@Rollback" Sheets | 2019-04-01 | Nazira Kamal / Leon Lim
1.2 | Fixed missing sheets cosmetic touch up. | 2019-04-12 | Leon Lim
1.3 | Realigned & corrected formulas | 2019-05-24 | Leon Lim
1.4 | Tower Reviewer updated | 2020-06-26 | Mahesh Sonwane
1.5 | Tabs added for BO and OAT | 2020-09-07 | Mahesh Sonwane
1.6 | Added tooltips, ChangeInfo Tab added, PIR Integrated within CIP, PONR added, Removed obsolete "Postponed@Cancelled" & "Unsuccessful@Rollback" Sheets | 2021-03-11 | Mahesh Sonwane
1.7 | Added "Expected Results" on implementation and rollback tab | 2021-06-21 | Mahesh Sonwane
1.7.1 | Added " New PIR template" | 2021-10-29 | Praveen Kumar Modala
Design Notes |  | (press "+"-sign to show hidden rows)
1. Assumption is Task Implementer is identified on or near to Implemenatation date or can be confirmed only on Implementation day. 2. Generally task starts & ends on same date. Except crossing over at midnight. Thus auto copy Start date into End Date to reduce manual entry work. End Date copied by formula can be overwritten manually if different.
Work Instruction |  | (press "+"-sign to show hidden rows)
Save the template with naming convention "CRQ ImPlan (Change#-Short Description).xlsx" 0. ALL SECTIONS OF THE TEMPLATE ARE MANDATORY TO BE FILLED 1. Define the steps required for the full implementation plan (inclusive of any pre readiness or pre-requisite checks) along with post implmentation tasks, under the respective applicable sections. Rows can be added or deleted as applicable. 2. Fill in the estimated start/end date/time plan. 3. Reviewer to review plan captured. 4. Implementer to complete with the actual start/end date/time. 5. Reviewer to review the actual implementation status. 6. For any BC5 application, a joint walkthrough must be completed with the respective PSS owner 7. Set to Final status before storing the final version of file 8. During execution the actual date/times of the start and finish of a task must be captured 9. Follow the Instructions on "BO task Details" tab and fill BO form if a blackout is required for the change 10. Fill the "OAT Approval from" if the change is related to RFS and needs OAT - There must not be any deviation to the approved Implementation or Backout Plans, even if requested by customer. - STOP, or consult Reviewer / Tower Lead / SDM if in doubt or pressured before or during the implementation. - Hidden row & column not allowed in "CRQ Implementation Plan", for clarity.
Additional change steps in DOD not listed in approved Change Implementation Plan is not an authorised change. Reject it.
Because the steps and it's associated rollback plan is not reviewed for approval. All change steps must be complete & recorded in this template prior to seeking approval.

## ChangeInfo
Change Implementation Plan (CIP)
This Change's ID
Stage Of The Change |  |  | PROD: This change has been tested on a non-production environment, and will now be applied to production. As evidence: give the ticket number that was used on the non-production environment, or add any release notes.
Comments : Mandatory to provide justification if no testing done | [5 empty] | Do not fill for Standard Changes
|  | Change Timelines (HKT) |  |  |  | Note : only use HKT timezone in install plan
| Start Date And Time (HKT) |  |  | End Date And Time (HKT) | Duration
Implementation Timeline (Exclude Pre-task and backout) | [6 empty] | <<======Do not fill data in this row manually / overwrite formulas
Planned Outage Timeline | NA |  |  | N/A | not applicable |  | <<======Manually Update Outage Start date and End date in MM/DD/YYYY HH:MM, if applicable
Note on M10: Author: Autocalculated
Note on A11: Author: to cross check we don’t cross monday
Note on A12: Author: to look out for critical timeline

## Data Validation (hidden)
Tier1 | Tier2 | [16 empty] | Tier3
Tier1 List | Application | Infra_Database | Infra_Storage | Infra_Network | Infra_Cloud | Infra_Voice | Infra_Web_Services | Infra_Platforms | Infra_Integration_Services | Infra_GRID | End_User_Services | Infra_DataCentre | User | Vendor_InternalAtos | Vendor_External | Security | Choose_an_option | ApplicationChange | ApplicationHumanError | ApplicationSoftwareDesign | ApplicationCapacity | ApplicationInconclusive | Infra_DatabaseChange | Infra_StorageChange | Infra_NetworkChange | Infra_CloudChange | Infra_VoiceChange | Infra_Web_ServicesChange | Infra_PlatformsChange | Infra_Integration_ServicesChange | Infra_GRIDChange | End_User_ServicesChange | Infra_DatabaseHumanError | Infra_StorageHumanError | Infra_NetworkHumanError | Infra_CloudHumanError | Infra_VoiceHumanError | Infra_Web_ServicesHumanError | Infra_PlatformsHumanError | Infra_Integration_ServicesHumanError | Infra_GRIDHumanError | End_User_ServicesHumanError | Infra_DatabaseInfrastructureDesign | Infra_StorageInfrastructureDesign | Infra_NetworkInfrastructureDesign | Infra_CloudInfrastructureDesign | Infra_VoiceInfrastructureDesign | Infra_Web_ServicesInfrastructureDesign | Infra_PlatformsInfrastructureDesign | Infra_Integration_ServicesInfrastructureDesign | Infra_GRIDInfrastructureDesign | End_User_ServicesInfrastructureDesign | Infra_DatabaseCapacity | Infra_StorageCapacity | Infra_NetworkCapacity | Infra_CloudCapacity | Infra_VoiceCapacity | Infra_Web_ServicesCapacity | Infra_PlatformsCapacity | Infra_Integration_ServicesCapacity | Infra_GRIDCapacity | End_User_ServicesCapacity | Infra_DatabaseMaintenance | Infra_StorageMaintenance | Infra_NetworkMaintenance | Infra_CloudMaintenance | Infra_VoiceMaintenance | Infra_Web_ServicesMaintenance | Infra_PlatformsMaintenance | Infra_Integration_ServicesMaintenance | Infra_GRIDMaintenance | End_User_ServicesMaintenance | Infra_DatabaseInconclusive | Infra_StorageInconclusive | Infra_NetworkInconclusive | Infra_CloudInconclusive | Infra_VoiceInconclusive | Infra_Web_ServicesInconclusive | Infra_PlatformsInconclusive | Infra_Integration_ServicesInconclusive | Infra_GRIDInconclusive | End_User_ServicesInconclusive | Infra_DatabaseHardware | Infra_StorageHardware | Infra_NetworkHardware | Infra_CloudHardware | Infra_VoiceHardware | Infra_Web_ServicesHardware | Infra_PlatformsHardware | Infra_Integration_ServicesHardware | Infra_GRIDHardware | End_User_ServicesHardware | Infra_DataCentreChange | Infra_DataCentreHumanError | Infra_DataCentreInfrastructureDesign | Infra_DataCentreCapacity | Infra_DataCentreMaintenance | Infra_DataCentreInconclusive | Infra_DataCentreHardware | Infra_DataCentreFacility | UserChange | UserHuman Error | UserCapacity | Vendor_InternalAtosChange | Vendor_InternalAtosHumanError | Vendor_InternalAtosSoftwareDesign | Vendor_InternalAtosCapacity | Vendor_InternalAtosInconclusive | Vendor_InternalAtosHardware | Vendor_InternalAtosInfrastructureDesign | Vendor_ExternalChange | Vendor_ExternalHumanError | Vendor_ExternalSoftwareDesign | Vendor_ExternalCapacity | Vendor_ExternalInconclusive | Vendor_ExternalHardware | Vendor_ExternalInfrastructureDesign | SecuritySecurity | Choose_an_optionChooseanoption | Failure Code | Incident Priority
Choose_an_option | Change | Change | Change | Change | Change | Change | Change | Change | Change | Change | Change | Change | Change | Change | Change | Security | Choose an option | Coding Error | Lack of Diligence | Application Software Bug/Defect | Insufficient Capacity Planning | Insufficient Data Logs | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Lack of Diligence | Lack of Diligence | Lack of Diligence | Lack of Diligence | Lack of Diligence | Lack of Diligence | Lack of Diligence | Lack of Diligence | Lack of Diligence | Lack of Diligence | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Operating System Bug/Defect | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Capacity Planning | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient Patch Management | Insufficient data logs | Insufficient data logs | Insufficient data logs | Insufficient data logs | Insufficient data logs | Insufficient data logs | Insufficient data logs | Insufficient data logs | Insufficient data logs | Insufficient data logs | Hardware Failure | Hardware Failure | Hardware Failure | Hardware Failure | Hardware Failure | Hardware Failure | Hardware Failure | Hardware Failure | Hardware Failure | Hardware Failure | Infrastructure Script/Query Error | Lack of Diligence | Operating System Bug/Defect | Insufficient Capacity Planning | Insufficient Patch Management | Insufficient data logs | Hardware Failure | Cooling Outages | Coding Error | Lack of Diligence | Insufficient Capacity Planning | Coding Error | Lack of Diligence | Application Software Bug/Defect | Insufficient Capacity Planning | Insufficient Data Logs | Hardware Failure | Operating System Bug/Defect | Coding Error | Lack of Diligence | Application Software Bug/Defect | Insufficient Capacity Planning | Insufficient Data Logs | Hardware Failure | Operating System Bug/Defect | Media Handling | Choose an option | Choose an option | Choose an option
Application | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error | Human Error |  |  | Design Gap | Knowledge Gap | Configuration | Special Events | Inability to Simulate | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Knowledge Gap | Configuration | Configuration | Configuration | Configuration | Configuration | Configuration | Configuration | Configuration | Configuration | Configuration | Special Events | Special Events | Special Events | Special Events | Special Events | Special Events | Special Events | Special Events | Special Events | Special Events | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Maintenance/Housekeeping | Inability to Simulate | Inability to Simulate | Inability to Simulate | Inability to Simulate | Inability to Simulate | Inability to Simulate | Inability to Simulate | Inability to Simulate | Inability to Simulate | Inability to Simulate | [10 empty] | Design Gap | Knowledge Gap | Configuration | Special Events | Maintenance/Housekeeping | Inability to Simulate |  | Power Disruptions | Design Gap | Knowledge Gap | Special Events | Design Gap | Knowledge Gap | Configuration | Special Events | Inability to Simulate |  | Configuration | Design Gap | Knowledge Gap | Configuration | Special Events | Inability to Simulate |  | Configuration | Information Classification |  | Backed Out (Rolled Back) | Critical
Infra_Database | Software Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Infrastructure Design | Capacity | Software Design | Software Design |  |  | Inadequate Impact Analysis |  | Obsolescence |  | Product Out of Support | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | Inadequate Impact Analysis | [10 empty] | Obsolescence | Obsolescence | Obsolescence | Obsolescence | Obsolescence | Obsolescence | Obsolescence | Obsolescence | Obsolescence | Obsolescence | [20 empty] | Product Out of Support | Product Out of Support | Product Out of Support | Product Out of Support | Product Out of Support | Product Out of Support | Product Out of Support | Product Out of Support | Product Out of Support | Product Out of Support | [10 empty] | Inadequate Impact Analysis |  | Obsolescence |  |  | Product Out of Support |  |  | Inadequate Impact Analysis |  |  | Inadequate Impact Analysis |  | Obsolescence |  | Product Out of Support |  | Obsolescence | Inadequate Impact Analysis |  | Obsolescence |  | Product Out of Support |  | Obsolescence | Access Control |  | Partial Implementation | High
Infra_Storage | Capacity | Capacity | Capacity | Capacity | Capacity | Capacity | Capacity | Capacity | Capacity | Capacity | Capacity | Capacity |  | Capacity | Capacity |  |  | Inadequate Change Plans |  | Design Gap |  |  | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | Inadequate Change Plans | [10 empty] | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | Design Gap | [40 empty] | Inadequate Change Plans |  | Design Gap | [5 empty] | Inadequate Change Plans |  |  | Inadequate Change Plans |  | Inadequate/absence SLA/OLA |  |  |  | Design Gap | Inadequate Change Plans |  | Inadequate/absence SLA/OLA |  |  |  | Design Gap | Malware |  | Caused Incident | Medium
Infra_Network | Inconclusive | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance |  | Inconclusive | Inconclusive |  |  | Unauthorised Change |  |  |  |  | Unauthorised Change | Unauthorised Change | Unauthorised Change | Unauthorised Change | Unauthorised Change | Unauthorised Change | Unauthorised Change | Unauthorised Change | Unauthorised Change | Unauthorised Change | [10 empty] | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | Infrastructure Script/Query Error | [40 empty] | Unauthorised Change |  | Infrastructure Script/Query Error | [5 empty] | Unauthorised Change |  |  | Unauthorised Change |  | Design Gap |  |  |  | Infrastructure Script/Query Error | Unauthorised Change |  | Design Gap |  |  |  | Infrastructure Script/Query Error | Vulnerability Management |  |  | Service At Risk (S@R)
Infra_Cloud | Choose an option | Inconclusive | Inconclusive | Inconclusive | Inconclusive | Inconclusive | Inconclusive | Inconclusive | Inconclusive | Inconclusive | Inconclusive | Inconclusive |  | Hardware | Hardware |  |  | Inadequate Requirements Gathering |  |  |  |  | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | Inadequate Requirements Gathering | [60 empty] | Inadequate Requirements Gathering | [7 empty] | Inadequate Requirements Gathering |  |  | Inadequate Requirements Gathering | [6 empty] | Inadequate Requirements Gathering | [6 empty] | Network Security Management |  |  | Low
Infra_Voice |  | Hardware | Hardware | Hardware | Hardware | Hardware | Hardware | Hardware | Hardware | Hardware | Hardware | Hardware |  | Infrastructure Design | Infrastructure Design |  |  | Deployment |  |  |  |  | Deployment | Deployment | Deployment | Deployment | Deployment | Deployment | Deployment | Deployment | Deployment | Deployment | [60 empty] | Deployment | [7 empty] | Deployment |  |  | Deployment | [6 empty] | Deployment | [6 empty] | Acceptable Us
Infra_Web_Services |  | Choose an option | Choose an option | [8 empty] | Facility | [5 empty] | Operational Readiness |  |  |  |  | Operational Readiness | Operational Readiness | Operational Readiness | Operational Readiness | Operational Readiness | Operational Readiness | Operational Readiness | Operational Readiness | Operational Readiness | Operational Readiness | [60 empty] | Operational Readiness
Infra_Platforms
Infra_Integration_Services
Infra_GRID | Yes |  | Tower |  | Stage Of the Change
End_User_Services | No |  | Data Centre |  | TEST: This change is being applied to a Dev/Test/QA/Staging environment and will not affect any production CI In the comments-box you may optionally list any release notes.
Infra_DataCentre |  |  | Windows |  | PROD: This change has been tested on a non-production environment, and will now be applied to production. As evidence: give the ticket number that was used on the non-production environment, or add any release notes.
User |  |  | UNIX |  | NO-TEST: This change will be applied to production, but the capability to simulate or test has been very limited or non-existent. As comments: explain why it could not be tested, is a test environment available, what mitigation is in place? Do we have a successful history for this change (Provide Evidence tickets)
Vendor_InternalAtos |  |  | Database
Vendor_External |  |  | Storage
Security |  |  | Backup
Enterprise Monitoring
Tooling
Project Management
Enterprise Batch Mgmt
Main Frame

## Implementation Plan
ATOS High Level - Change Implementation Plan
Task | Task Description | Host, Server or Environment name (if applicable) | Task Dependency if applicable | Task Owner | Tower/Domain | Remedy Group | Planned Start Date | Planned Start Time HKT | Planned End Date | Planned End Time HKT | Planned Duration (hour:min) | Expected Outcome | Actual Start Date | Actual Start Time HKT | Actual End Date | Actual End Time HKT | Actual Duration (hour:min) | Task Implementer (update during CRQ execution) | Comments or Notes
Pre-Change Activities *** MANDATORY SECTION
PRE1 | Withdraw EID password from Onevault. | hklvdpapp071 a.supp.<Bank Id> | NA | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG INFRA SERVER - UNIX - ATOS PROD TSO CHG AO-SG MR DBA TSO CHG <Application PSS team SNOW Group> | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG INFRA SERVER - UNIX - ATOS PROD TSO CHG AO-SG MR DBA TSO CHG <Application PSS team SNOW Group> | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG INFRA SERVER - UNIX - ATOS PROD TSO CHG AO-SG MR DBA TSO CHG STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-29 | 14:30 | 2022-12-29 | 15:00 | 0.020833 | ID withdrawn
PRE2 | Hold backup job if any for VM hklvdpapp071. | hklvdpapp071 | NA | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | 2022-12-29 | 15:00 | 2022-12-29 | 15:30 | 0:30 | backup hold
PREX | GO / NO GO CHECKPOINT | hklvdpapp071 | NA | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-29 | 15:30 | 2022-12-29 | 16:00 | 0.020833 | Plan ready to go
Identify the Point of No Return *** MANDATORY SECTION
PONR Step# | Not Applicable
Implementation Steps *** MANDATORY SECTION
IMP1 | Asssign new disks as below - Platform team (Linux) to add new disks as per below Size to VM - hklvdpapp071 (Total -14TB) hkmg-db03-thn-tx-l-ldev0012-mongodb - 4TB hkmg-db03-thn-tx-l-ldev0011-mongodb - 5TB hkmg-db03-thn-tx-l-ldev0013-mongodb - 5TB Create/Configure Filesystem. Once 14TB File system created / configured then provide File system details to Backup Team & Database Team. | hklvdpapp071 | PREX | INFRA SERVER - UNIX - ATOS PROD TSO CHG INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG -Standby support | INFRA SERVER - UNIX - ATOS PROD TSO CHG INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG -Standby support | INFRA SERVER - UNIX - ATOS PROD TSO CHG INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG -Standby support | 2022-12-29 | 16:00 | 2022-12-29 | 17:00 | 0.041667 | Access to vCenter
IMP2 | Scan the disks in the server. If the disks are not detected in the mentioned servers, The application team need to stop the application followed by DB stop , reboot the host and then re-scan the disks. Allocate to below FS: /orafra = extend by 2 TB /oradata = extend by 12 TB | hklvdpapp071 | IMP1 | INFRA SERVER - UNIX - ATOS PROD TSO CHG | INFRA SERVER - UNIX - ATOS PROD TSO CHG | INFRA SERVER - UNIX - ATOS PROD TSO CHG | 2022-12-29 | 17:00 | 2022-12-29 | 18:00 | 1:00
IMP3 | Update /etc/hosts file with below entries 1) Take backup cp -p /etc/hosts /tmp/hosts_bkup 2) Update /etc/hosts file with below entries. # Data Domain - VLAN4019 192.168.216.12 AOHKDD05P aohkdd05p aohkdd05p.hk.standardchartered.com 192.168.216.13 AOHKDD06P aohkdd06p aohkdd06p.hk.standardchartered.com 192.168.216.16 AOHKDD07P aohkdd07p aohkdd07p.hk.standardchartered.com 192.168.216.23 AOHKDD08P aohkdd08p aohkdd08p.hk.standardchartered.com 192.168.216.1 AOHKDD09P aohkdd09p aohkdd09p.hk.standardchartered.com 192.168.216.2 AOHKDD10P aohkdd10p aohkdd10p.hk.standardchartered.com 192.168.216.3 AOHKDD11P aohkdd11p aohkdd11p.hk.standardchartered.com 192.168.216.4 AOHKDD12P aohkdd12p aohkdd12p.hk.standardchartered.com 192.168.216.5 AOHKDD13P aohkdd13p aohkdd13p.hk.standardchartered.com # Storage node - VLAN 4019 192.168.216.14 HKLVIPAPP028 hklvipapp028 hklvipapp028.hk.standardchartered.com 192.168.216.15 HKLVIPAPP029 hklvipapp029 hklvipapp029.hk.standardchartered.com 192.168.216.11 HKLPIPBCK07 hklpipbck07 hklpipbck07.hk.standardchartered.com 192.168.216.20 HKLPIPBCK03 hklpipbck03 hklpipbck03.hk.standardchartered.com 192.168.216.21 HKLPIPBCK05 hklpipbck05 hklpipbck05.hk.standardchartered.com 192.168.216.22 HKLPIPBCK06 hklpipbck06 hklpipbck06.hk.standardchartered.com 192.168.216.38 HKLPIPBCK011 hklpipbck011 hklpipbck011.hk.standardchartered.com 192.168.216.39 HKLPIPBCK012 hklpipbck012 hklpipbck012.hk.standardchartered.com 192.168.216.27 HKLVIPAPP036 hklvipapp036 hklvipapp036.hk.standardchartered.com 192.168.216.28 HKLVIPAPP037 hklvipapp037 hklvipapp037.hk.standardchartered.com | hklvdpapp071 | IMP2 | INFRA SERVER - UNIX - ATOS PROD TSO CHG | INFRA SERVER - UNIX - ATOS PROD TSO CHG | INFRA SERVER - UNIX - ATOS PROD TSO CHG | 2022-12-29 | 18:00 | 2022-12-29 | 19:00 | 1:00
IMP4 | Proximity team to load tapes | hklvdpapp071 | IMP3 | INFRA SERVER-GBL OSV AO HK PROXIMITY TSO CHG | INFRA SERVER-GBL OSV AO HK PROXIMITY TSO CHG | INFRA SERVER-GBL OSV AO HK PROXIMITY TSO CHG | 2022-12-29 | 19:00 | 2022-12-29 | 20:00 | 1:00 | Mount Tapes
IMP5 | Bcakup team to Share JUNE 2022 MLY Restore Parameters to database Team - Server HKLPDSS2B002 - instance - POHK2CCD | hklvdpapp071 | IMP4 | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | 2022-12-29 | 20:00 | 2022-12-29 | 21:00 | 1:00
IMP6 | As per the Restore Parameters provided by Backup team & file system created/Configured by Linux perform Database restore. | hklvdpapp071 | IMP5 | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | 2022-12-29 | 21:00 | 2022-12-30 | 21:00 |  | DB restore
IMP7 | Export these 6 tables to dump file (DUMP_SEP_2022.dmp) : NOTE: See the steps in Data_restoration_AIG_SEP.txt to export. S2BV4CDS_ADMIN.CDL_WKFL_LOGGER S2BV4CDS_ADMIN.CDL_WORKFLOW S2BV4CDS_ADMIN.CDL_WKFL_PYMT_AUTHMATRIX S2BV4CDS_ADMIN.PYMT_TRANS S2BV4CDS_ADMIN.CDL_AUDIT S2BV4CDS_ADMIN.PYMT_BATCH | hklvdpapp071 | NA | AO-SG MR DBA TSO CHG
IMP8 | Drop current database, perform database restoration and recovery from RMAN backup of JUNE 2022 | hklvdpapp071 | IMP6 | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | 2022-12-29 | 21:00 | 2022-12-31 | 5:00
IMP9 | Export these 6 tables to dump file (DUMP_JUNE_2022.dmp): NOTE: See the steps in Data_restoration_AIG_JUN.txt to export. S2BV4CDS_ADMIN.CDL_WKFL_LOGGER S2BV4CDS_ADMIN.CDL_WORKFLOW S2BV4CDS_ADMIN.CDL_WKFL_PYMT_AUTHMATRIX S2BV4CDS_ADMIN.PYMT_TRANS S2BV4CDS_ADMIN.CDL_AUDIT S2BV4CDS_ADMIN.PYMT_BATCH | hklvdpapp071 | IMP8 | AO-SG MR DBA TSO CHG
IMP10 | Proximity team to load tapes | hklvdpapp071 | IMP3 | INFRA SERVER-GBL OSV AO HK PROXIMITY TSO CHG | INFRA SERVER-GBL OSV AO HK PROXIMITY TSO CHG | INFRA SERVER-GBL OSV AO HK PROXIMITY TSO CHG | 2022-12-29 | 19:00 | 2022-12-29 | 20:00 | 1:00 | Mount Tapes
IMP11 | Bcakup team to Share MARCH 2022 MLY Restore Parameters to database Team - Server HKLPDSS2B002 - instance - POHK2CCD | hklvdpapp071 | IMP10 | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG
IMP12 | As per the Restore Parameters provided by Backup team & file system created/Configured by Linux perform Database restore. | hklvdpapp071 | IMP11 | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG
IMP13 | Drop current database, perform database restoration and recovery from RMAN backup of MARCH 2022 | hklvdpapp071 | IMP12 | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG
IMP14 | Perform import tables from dump file taken on step IMP7 into different table names with suffix *_SEP as per the steps in Data_restoration_AIG_SEP.txt followed by create indexes and GRANT execution | hklvdpapp071 | IMP7 | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG
IMP15 | Perform import tables from dump file taken on step IMP9 into different table names with suffix *_JUN as per the steps in Data_restoration_AIG_JUN.txt followed by create indexes and GRANT execution | hklvdpapp071 | IMP9 | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG | AO-SG MR DBA TSO CHG
IMP16 | Application team to perform final Verification. | hklvdpapp071 | IMP15 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-31 | 5:00 | 2022-12-31 | 6:00
IMP17 | Hold backup job if any for VM hklvdpapp071. | hklvdpapp071 | IMP13 | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG | 2022-12-31 | 6:00 | 2022-12-31 | 7:00 |  | backup release
IMP18 | GO / NO GO CHECKPOINT | hklvdpapp071 | IMP9 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-31 | 7:00 | 2022-12-31 | 8:00 |  | Plan ready to go
Post Implementation Testing *** MANDATORY SECTION
PIT1 | Verify that all tasks are completed successfully. | hklvdpapp071 | IMPX | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-31 | 8:00 | 2022-12-31 | 9:00 |  | Verified
PITX | GO / NO GO CHECKPOINT | hklvdpapp071 | PIT2 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-31 | 9:00 | 2022-12-31 | 10:00 |  | Plan ready to go
Change Exit Criteria *** MANDATORY SECTION
EXT1 | Upload the completed Implementation plan to the ticket along with the PIT | hklvdpapp071 | PITX | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-31 | 10:00 | 2022-12-31 | 10:30 |  | Uploaded | [6 empty] | Click Here to Download the PIT Checklist
EXT2 | Communicate Completion | hklvdpapp071 | EXT1 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-31 | 10:30 | 2022-12-31 | 11:00 |  | Communicated
Change Closure *** MANDATORY SECTION
END | Close out Change in Remedy * | hklvdpapp071 | EXT2 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | STRAIGHT2BANKV4-CASH PROD TSO CHG | 2022-12-31 | 11:00 | 2022-12-31 | 11:30 |  | Closed
* | Mandatory Section/Step
Management Data | [10 empty] | Planned | [5 empty] | Actual
| Pre-Change Activities Duration | [9 empty] | 1:30 | [5 empty] | 0:00 | h:mm
| Implementation Steps Duration | [9 empty] | 6:00 | [5 empty] | 0:00 | h:mm
| Post Implementation Testing Duration | [9 empty] | 0:00 | [5 empty] | 0:00 | h:mm
| Change Exit Criteria Duration | [9 empty] | 0:00 | [5 empty] | 0:00 | h:mm
| Change Closure Duration | [9 empty] | 0:00 | [5 empty] | 0:00 | h:mm
| Total Change Duration | [9 empty] | 7:30 | [5 empty] | 0:00 | h:mm
Reviewed by Tower Head
Name: Nitin Khope
Date and time :Wed 28/11/2022 4:00 PM HKT
Reviewed by SME / Lead
Name: Vijay Dasari
Date and time :Wed 28/11/2022 3:00 PM HKT
Formulas:
Planned End Date = IF(ISBLANK([Planned Start Date]),"",[Planned Start Date])
Note on D2: List the dependant task from the plan. If cell is blank can be done in parallel
Note on E2: If the task applies to a particular Server, or Environment, please specifiy
Note on F2: Area Responsible (i.e. Wintel, Network, Retail Banking, Private Banking etc)
Note on L2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.
Note on M2: Author: Mandatory Field : Update the expected outcome of the task performed
Note on R2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Purpose Reply: PONR is a single step to be identified and mentioned in cell#B9 after which the change can not be rolled back
Note on A34: Author: move to Change closure part
Note on A35: Author: move to Change closure part

## DASD
Server Name | IP | Mount Point name (Linux/Unix) | Current Size (Linux/Unix) | Extend by | Permission(Unix/Linux) | Note : Existing FS /New FS?
hklvdpapp071 | 10.7.148.112 | /orafra | 270 GB | 2 TB | Linux | Existing FS
hklvdpapp071 | 10.7.148.112 | /oradata | 550 GB | 12 TB | Linux | Existing FS

## RollBack Plan
ATOS High Level - Change Implementation Plan
Task | Task Description | Host, Server or Environment name (if applicable) | Task Dependency if applicable | Task Owner | Tower/Domain | Remedy Group | Planned Start Date | Planned Start Time HKT | Planned End Date | Planned End Time HKT | Planned Duration (hour:min) | Expected Outcome | Actual Start Date | Actual Start Time HKT | Actual End Date | Actual End Time HKT | Actual Duration (hour:min) | Task Implementer (update during CRQ execution) | Comments or Notes
Pre-Back Out Activities *** MANDATORY SECTION
PRE1 | Withdraw EID password from Onevault. | hklvdpapp071 a.supp.<Bank Id> | NA | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG <Linux team SNOW Group> <Database team SNOW Group> <Application PSS team SNOW Group> | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG <Linux team SNOW Group> <Database team SNOW Group> <Application PSS team SNOW Group> | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG <Linux team SNOW Group> <Database team SNOW Group> <Application PSS team SNOW Group> | [5 empty] | Withdrawn | 2022-12-31 | 7:00 | 2022-12-31 | 7:30 | #REF!
PREX | GO / NO GO CHECKPOINT | hklvdpapp071 | NA | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | [5 empty] | Plan Ready To Go | 2022-12-31 | 7:00 | 2022-12-31 | 7:30 | #REF!
Back Out Steps *** MANDATORY SECTION
IMP1 | If any error after database restoration then work together to discuss & resolve error. | hklvdpapp071 | PREX | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG <Linux team SNOW Group> <Database team SNOW Group> <Application PSS team SNOW Group> | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG <Linux team SNOW Group> <Database team SNOW Group> <Application PSS team SNOW Group> | INFRA SERVER-ALL GBL TS PSRV VIRTATOS SUP TSO CHG INFRA-STORAGE-ATOS-BACKUP-PROD-TSO CHG <Linux team SNOW Group> <Database team SNOW Group> <Application PSS team SNOW Group> | [5 empty] | Reimported | 2022-12-31 | 7:30 | 2022-12-31 | 10:30 | 3:00
Post Back Out Testing *** MANDATORY SECTION
PIT1 | Check all IMP tasks complete | hklvdpapp071 | IMP1 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | [5 empty] | Completed | 2022-12-31 | 10:30 | 2022-12-31 | 11:00 | 0:30
PITX | GO / NO GO CHECKPOINT | hklvdpapp071 | PIT1 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | [5 empty] | Plan ready to go | 2022-12-31 | 11:00 | 2022-12-31 | 11:15 | 0:15
Change Exit Criteria *** MANDATORY SECTION
EXT1 | Alert Review (If Black Out Initiated) | [11 empty] | 2022-12-31 | 11:15 | 2022-12-31 | 11:30
EXT2 | Reminder Complete PIR template | hklvdpapp071 | PITX | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | [5 empty] | Uploaded | 2022-12-31 | 11:15 | 2022-12-31 | 11:30 | 0:15
EXT3 | Communicate Completion | hklvdpapp071 | EXT2 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | [5 empty] | Communicated | 2022-12-31 | 11:15 | 2022-12-31 | 11:30
Change Closure *** MANDATORY SECTION
END | Close out Change in Remedy * | hklvdpapp071 | EXT3 | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | <Application PSS Team SNOW Group> | [5 empty] | Closed | 2022-12-31 | 11:15 | 2022-12-31 | 11:30 | 0:15
* | Mandatory Section/Step
Management Data | [9 empty] | Planned | 0:00 |  | Hour:Minute |  |  | Actual | #REF! | Hour:Minute
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List the dependant task from the plan. If cell is blank can be done in parallel
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the task applies to a particular Server, or Environment, please specifiy
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Area Responsible (i.e. Wintel, Network, Retail Banking, Private Banking etc)
Note on L2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.
Note on M2: Author: Author: Mandatory Field : Update the expected outcome of the task performed
Note on R2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.

## Server List
hklvdpapp071
hklvdpapp071 having disks assigned from datastore - hkmg-db03-thn-tx-l-ldev0012-mongodb
Request - 14TB
Temporary - 30days
hklvdpapp071
Platform team to add new disks as per below Size to VM - hklvdpapp071
hkmg-db03-thn-tx-l-ldev0012-mongodb - 4TB
hkmg-db03-thn-tx-l-ldev0011-mongodb - 5TB
hkmg-db03-thn-tx-l-ldev0013-mongodb - 5TB

## BO task Details
Blackout Template
All information are mandatory to be filled.
No FQDN in the Server Name column. Only Hostname.
Blackout Date & Time must follow this format: dd/mm/yyyy hh:mm
Blackout Time must follow this format: 24-hours and in HKT time zone.
Blackout will not be performed/extended if less than 30 minutes prior Blackout Start Time/End Time.
Blackout Date & Time must be within the Change Request window.
For Any Change requiring Support From NSM must have a task in Remedy ticket
If ad-hoc requests of Blackout removal is required it must be done with at least 30 minutes of buffer time, provided the Change end time is more than 2 hours away
BO Start Date & time (dd/mm/yyyy hh:mm HKT) | BO End Date & time (dd/mm/yyyy hh:mm HKT) | Server Name | IP Address | Host Type
NA | NA | NA | NA | NA

## OAT Approval Form
This tab is only required for changes related RFS
| RFS # |  |  |  |  | Yes
| TCC1 PLATFORM CONTACT |  |  |  |  | No
TCC1 PROJECT MANAGER CONTACT
NO | HOSTNAME | IP ADDRESS | OS PLATFORM | DMZ (YES/NO) | ADDITIONAL APPLICATION MONITORING (if required)
1 | hkepipvdi08a | #REF! | #REF! | No | for ex, PostgresSQL 12 ,
2 | hkepipvdi09a | #REF! | #REF! | No
3 | hkepipvdi10a | #REF! | #REF! | No
4 | hkepipvdi11a | #REF! | #REF! | No
5 | hkepipvdi12a | #REF! | #REF! | No
6 | hkepipvdi13a | #REF! | #REF! | No
7 | hkepipvdi14a | #REF! | #REF! | No
8 | hkepipvdi15a | #REF! | #REF! | No
9 | hkepipvdi16a | #REF! | #REF! | No
10 | hkepipvdi17a | #REF! | #REF! | No
11 | hkepipvdi18 | #REF! | #REF! | No
12 | hkepipvdi19 | #REF! | #REF! | No
13 | hkepipvdi20 | #REF! | #REF! | No
14 | hkepipvdi21 | #REF! | #REF! | No
15 | hkepipvdi22 | #REF! | #REF! | No
16 | hkepipvds016 | #REF! | #REF! | No
17 | hkepipvds017 | #REF! | #REF! | No
18 | hkepipvds020 | #REF! | #REF! | No
19 | hkepisvdi18 | #REF! | #REF! | No
20 | hkepisvdi19 | #REF! | #REF! | No
21 | hkepisvdi020 | #REF! | #REF! | No
22 | hkepisvdi021 | #REF! | #REF! | No
23 | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF!
26 | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF!
32 | #REF! | #REF! | #REF!
33 | #REF! | #REF! | #REF!
34 | #REF! | #REF! | #REF!
35 | #REF! | #REF! | #REF!

## Associated Docs
EMBED any Associated Documents or Instructions here
Item | Associated to CRQ ImPlan Step | Document

## PIR Form
POST IMPLEMENTATION REVIEW
Section 1. Base Ticket Information
BMC Remedy Change Number |  |  | Date PIR Initiated
Change Class: |  |  | Date of PIR Finalization
Change Title/Summary |  |  | PIR Required by Date
Change Coordinator Email |  |  | Tower Head Review by
Coordinator Group |  |  | SDM Review by
PIR Justification (Reason for the PIR) | Unauthorized Change |  | Change Management Review by
Section 2. Change Management Initial Review
Change Process Related Checks | Yes/No | Comments (Details of investigation or improvement needed)
Was change process followed?
Was the change Approved by ATOS CM?
Was the change started on time ? Check and record change timelines
Was the implementation plan followed?
Was the change Tested prior to implementation?
Was Pre-testing sufficient for this Change?
Was the backout plan used?
Was the backout done within the change window?
Was the change validated/tested after implementation?
Was any Third Party/Customer involvement during implementation ?
Description of the change Failure/ Issues (What went wrong with the implementation, what step/task/time etc)?
Service / System Affected (CI, Server name, Busines Unit, Function Org)
Impacted Service Information
Section 3. Investigation Details
3.1 Reason for Change Failure (Why did the Change Fail?)
3.2 Could this failure have been prevented? Yes/No, Describe how ?
3.3 Risk and Impact Assessment (How did the risk and impact deviate from expected? And impact on customer)
3.4 Categorization of reasons for Change Failure?
Comments -
Section 4. Improvement Actions
Process/ Technical Improvement Action
Action Description
Action Type
Action Owner
Action Owner Bank ID
Domain
Target Date
Action Status
Action Completed Date
Section 5. Lessons Learned
Section 6. Future Changes

## Data (hidden)
Emergency | ALL-GBL-TS-EUS-VDSATOS-PRJ | Failed Change | Kieran O'Mullan | Esther Chan | Mahesh Sonwane | Yes | Change to existing service | Technical Unforeseen | DR/Resiliiency Improvement | Not started
Expedited | ALL-GBL-TS-EUS-VDSATOS-SUP | Incident Caused by Change | Sanjay Pawar | Sreetharan | Mohd Fadli Mohd Ali | No | New Service Introduction | Hardware (e.g. Event Trigger) | Monitoring Improvement | In Progress
Latent | ALL-GBL-TS-PSRV-VIRTATOS-SUP | Partially Completed Change | OmPrakash Singh | Rajan Pujari | Praveen Kumar Modala | NA | Decommission of Service | Third Party - Atos (Vendor supplied Change/Atos implemented Change) | Permanent Fix | Completed
Normal | ASA-MY-TS-PSRV-VIRTATOS-SUP | Major Change | Vinayak, Vellore Arun | Vivegananthan | Sagar Potdar | Yes,but not fully |  | Third Party Customer | Preventive | Overdue
Standard | GBL-OSV-AO-HK CHANGE MGMT | Unauthorized Change | Geoffrey Chan | Alpesh Barot | Santosh Kumar Yadav |  |  | Security Access | Process Improvement
| GBL-OSV-AO-HK DCI | Backed Out | Bala Muthusami | Hui Sian | Komathi Jaya Krishnan |  |  | Software | Project Plan
| GBL-OSV-AO-HK ENTERPRISE SOL |  | Tsz Fung, Poon | Jason Chan |  |  |  | Process | Risk Proposal
| GBL-OSV-AO-HK MF CICS&COMM |  | Abhilash Bhaskaran |  |  |  |  | Human error | Workaround
| GBL-OSV-AO-HK MF DBA |  | Harjit Singh |  |  |  |  | Environmental (Power, heat, etc.) | Global Fix
| GBL-OSV-AO-HK MF OUTPUT |  | Md Faiz Sayed | ​ |  |  |  | Other | Feasibility Check
| GBL-OSV-AO-HK MF SERVER MGMT |  | Srikant Ande | [5 empty] | Other Improvement
| GBL-OSV-AO-HK MF SS HSP1 |  | Ali Kwok
| GBL-OSV-AO-HK MF SS HSP2 |  | Surendrababu
| GBL-OSV-AO-HK MF SS HSP3 |  | Anthony Man
| GBL-OSV-AO-HK MF SS HSP4 |  | Addy Chan | ​
| GBL-OSV-AO-HK MF SS OUTPUT |  | Kami Chan
| GBL-OSV-AO-HK MF STORAGE |  | Rohan Deshmukh
| GBL-OSV-AO-HK MR DR |  | Sujaikumar
GBL-OSV-AO-HK MR GDTS TENG
| GBL-OSV-AO-HK MR GEMS |  |  | ​
GBL-OSV-AO-HK MR STORAGE
GBL-OSV-AO-HK MR WINTEL
GBL-OSV-AO-HK NETWKR TECHCOORD
GBL-OSV-AO-HK PROBLEM MGMT
| GBL-OSV-AO-HK PROJECT MGMT |  |  | ​
GBL-OSV-AO-HK SECURITY
GBL-OSV-AO-HK VDI ADMIN
GBL-OSV-AO-IN MR AIX
GBL-OSV-AO-IN MR APP
GBL-OSV-AO-IN MR CITRIX
GBL-OSV-AO-IN MR DBA
GBL-OSV-AO-IN MR HORIZON
GBL-OSV-AO-IN MR LIN
GBL-OSV-AO-IN MR LIN NON-STD
GBL-OSV-AO-IN MR NBU-UNIX
GBL-OSV-AO-IN MR NET
GBL-OSV-AO-IN MR NSM
GBL-OSV-AO-IN MR SUN
GBL-OSV-AO-IN MR WAS
GBL-OSV-AO-IN MR WINTEL
GBL-OSV-AO-IN VDI ADMIN
GBL-OSV-AO-IN VIRTUALIZATION
GBL-OSV-AO-MY MF EMC
GBL-OSV-AO-MY MR EMC
GBL-OSV-AO-MY MR NSM
GBL-OSV-AO-MY MR TESTING
GBL-OSV-AO-MY SERVICE DESK
GBL-OSV-AO-MYIC DR
GBL-OSV-AO-MYIC MR DBA
GBL-OSV-AO-MYIC MR DR
GBL-OSV-AO-MYIC MR UNIX
GBL-OSV-AO-MYIC MR WINTEL
GBL-OSV-AO-MYIC NETWORK
GBL-OSV-AO-MYIC PROXIMITY
GBL-OSV-AO-PO MR TERADATA
GBL-OSV-AO-SG MR DBA
GBL-OSV-AO-SG MR DB-PROJECTS
GBL-OSV-AO-SG MR SERVER TEAM
GBL-OSV-ATOS HAAS
GBL-OSV-ATOS-HK MR UNIX TEAM C
GBL-OSV-ATOS-HK MR UNIX TEAM D
GBL-OSV-ATOS-HK MR UNIX TEAM E

## SDM VS APP (hidden)
| Business Functions / Domains | Atos SDM (Primary) | Atos SDM (Secondary)
| Retail Banking (exclude Core Banking), Private Banking and Wealth Management * | Helen Law | Anandh Ramasamy
| Retail Banking - Core Banking * | Anandh Ramasamy | Helen Law
| Transaction Banking and Global Banking * | Kathy Khoo (acting) | Esther Chan
| Group Functions, Data, Security, EUS * | Esther Chan | Kathy Khoo (acting)
* Please refer to the Business Service Report for the Applications under the different Domains, to identify the SDM to contact
| Mainframe LPAR | Atos SDM (Primary) | Atos SDM (Secondary)
| Applications in HSP1 | Helen Law | Anandh Ramasamy
| Applications in HSP2 | Kathy Khoo (acting) | Esther Chan
| Applications in HSP3 | Kathy Khoo (acting) | Esther Chan
| Applications in HSP4 | Anandh Ramasamy | Helen Law
GAI ID | Platform Service Offering | Atos SDM (primary) | Atos SDM (secondary)
| P2V - Atos Midrange VM Environment | Helen Law | Anandh Ramasamy
| AoD - Analytics on Demand | Helen Law | Anandh Ramasamy
| VDI - Virtual Desktop Infra | Kathy Khoo | Esther Chan