## Document Control
Document Control
Document Template Number | SCB Cocteau - Change - 0001
Change Number
Change Title
Change Short Description
Security Classification | For internal use
Version | 1.5
Status | Initial
Source | Atos
Document Date
Author(s)
Planned Data Reviewed Date
Planned Data Reviewer (s)
Actual Data Reviewed Date
Actual Data Reviewer (s)
Contents |  | (press "+"-sign to show hidden rows)
Sheet | Description
Document Control | Information pertaining to document control (this sheet)
Atos CRQ Impl Plan | Atos Change Request Implementation & Backout Plan
Target Readers for completed file |  | (press "+"-sign to show hidden rows)
Reader Group | Distribution Method
Respective Atos Tower / SMC
SDMs
List of Changes |  | (press "+"-sign to show hidden rows)
Version | Summar of Version Change | Date | Author(s)
0.1 | Initial Template | 01 Mar 2019 | Chris Harvey / Leon Lim
1.0 | Initial Release for general use | 2019-03-22 | Chris Harvey / Leon Lim
1.1 | Added "Postponed@Cancelled" & "Unsuccessful@Rollback" Sheets | 2019-04-01 | Nazira Kamal / Leon Lim
1.2 | Fixed missing sheets cosmetic touch up. | 2019-04-12 | Leon Lim
1.3 | Realigned & corrected formulas | 2019-05-24 | Leon Lim
1.4 | Tower Reviewer updated | 2020-06-26 | Mahesh Sonwane
1.5 | Tabs added for BO and OAT | 2020-09-07 | Mahesh Sonwane
Design Notes |  | (press "+"-sign to show hidden rows)
1. Assumption is Task Implementer is identified on or near to Implemenatation date or can be confirmed only on Implementation day. 2. Generally task starts & ends on same date. Except crossing over at midnight. Thus auto copy Start date into End Date to reduce manual entry work. End Date copied by formula can be overwritten manually if different.
Work Instruction |  | (press "+"-sign to show hidden rows)
Save the template with naming convention "CRQ ImPlan (Change#-Short Description).xlsx" 0. ALL SECTIONS OF THE TEMPLATE ARE MANDATORY TO BE FILLED 1. Define the steps required for the full implementation plan (inclusive of any pre readiness or pre-requisite checks) along with post implmentation tasks, under the respective applicable sections. Rows can be added or deleted as applicable. 2. Fill in the estimated start/end date/time plan. 3. Reviewer to review plan captured. 4. Implementer to complete with the actual start/end date/time. 5. Reviewer to review the actual implementation status. 6. For any BC5 application, a joint walkthrough must be completed with the respective PSS owner 7. Set to Final status before storing the final version of file 8. During execution the actual date/times of the start and finish of a task must be captured 9. Follow the Instructions on "BO task Details" tab and fill BO form if a blackout is required for the change 10. Fill the "OAT Approval from" if the change is related to RFS and needs OAT - There must not be any deviation to the approved Implementation or Backout Plans, even if requested by customer. - STOP, or consult Reviewer / Tower Lead / SDM if in doubt or pressured before or during the implementation. - Hidden row & column not allowed in "CRQ Implementation Plan", for clarity.
Additional change steps in DOD not listed in approved Change Implementation Plan is not an authorised change. Reject it.
Because the steps and it's associated rollback plan is not reviewed for approval. All change steps must be complete & recorded in this template prior to seeking approval.

## CRQ Implementation Plan
ATOS High Level - Change Implementation Plan
Task | Task Desription | Host, Server or Envonment name (if applicable) | Task Dependency if applicable | Task Owner | Tower/Domain | Remedy Group | Planned Start Date | Planned Start Time HKT | Planned End Date | Planned End Time HKT | Planned Duration (hour:min) | Actual Start Date | Actual Start Time HKT | Actual End Date | Actual End Time HKT | Actual Duration (hour:min) | Task Implementer (update during CRQ execution) | Comments or Notes
Pre-Change Activities *** MANDATORY SECTION
PRE1 | If your change requires Blackout please fill the BO template | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Value | N/A | N/A | N/A | N/A | #VALUE!
PRE2 | Withdraw e-id for the Servers HKLVDPAPP050 and hklvddapp068 | HKLVDPAPP050; ; hklvddapp068 | N/A | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
PRE3 | Confirm backup availability | N/A | PRE2 | GBL-OSV-AO-HK MR BUR | Atos | GBL OSV AO IN MR NBU | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
PREX | GO / NO GO CHECKPOINT | N/A | PRE4 | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
Implementation Steps *** MANDATORY SECTION
IMP1 | Restore Database (Sample Src DB :POHK10PS) via Networker to target database (Sample Tgt DB :AFASPE10 ) on FS /oradata in Pre Prod server(HKLVDPAPP050) Note: Refer sheet "DB Restore" for Source and Target DB names, Please refer the attached "31st March 2022.xlsx" for Database backup pieces information | HKLVDPAPP050 | PREX | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
IMP2 | As L0 RMAN backup is already Restored to target DB in Pre Prod to FS /oradata in change. | HKLVDPAPP050,hklvddapp068 | IMP1 | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
IMP3 | Provide 777 permission to the backup files to be transfered to dev servers, verify the data cut date in restored Prod server SELECT B.COUNTRY, A.BUSINESS_UNIT, A.PROCESS_DATE FROM SYSADM.PS_BUS_UNIT_TBL_GL A, SYSADM.PS_SCB_BU_CNTRYTBL B WHERE A.BUSINESS_UNIT = B.BUSINESS_UNIT; | HKLVDPAPP050 | IMP2 | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
IMP4 | Initiate file transfer Transfer the backup files to /oradata/CRQ000001537792 on hklvddapp068 test servers. | hklvddapp068 | IMP3 | GBL-ISCI-PSINFRA ALERTS | SCB | GBL-ISCI-PSINFRA ALERTS | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
IMP5 | Restore target DB from L0 backup location in step 4 to File system /oradata/CRQ000001537792 on hklvddapp068 test servers. Note: Refer Sheet "DB restore" Step Target test database for CDB/PDB names. | hklvddapp068 | IMP4 | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
IMP6 | Once restore is complete, Change database to No-archivelog mode.Bring up the Listeners | hklvddapp068 | IMP5 | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
IMP7 | Validate Test database if the secured data is correct and perform basic sanity check | hklvddapp068 | IMP6 | GBL-ISCI-PSINFRA ALERTS | SCB | SS team | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
IMP8 | Drop Target database (Sample Tgt DB : AFASPE10 ) on Pre Prod(HKLVDPAPP050) server and proceed to restore next instances | HKLVDPAPP050 | IMP7 | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
Post Implementation Testing *** MANDATORY SECTION
PIT1 | Ensure all DBs are restored correctly CDB names as below (Sample Tgt DB : AFASPE10) | hklvddapp068 | IMP8 | GBL-ISCI-PSINFRA ALERTS | SCB | SS team | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
PITX | GO / NO GO CHECKPOINT | N/A | PIT1 | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00 | [6 empty] | Must be completed before stepping out of the change
Change Exit Criteria *** MANDATORY SECTION
EXT1 | Refer "BO task details" tab for Alert Review (if blackout initiatied) *
EXT2 | Communicate Completion | N/A | PITX | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT
Change Closure *** MANDATORY SECTION
END | Close out Change in Remedy * | N/A | EXT2 | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT
* | Mandatory Section/Step
Management Data | [10 empty] | Planned |  |  |  |  | Actual
| Pre-Change Activities Duration | [9 empty] | 105:00 |  |  |  |  | #VALUE! | h:mm
| Implementation Steps Duration | [9 empty] | 245:00 |  |  |  |  | 0:00 | h:mm
| Post Implementation Testing Duration | [9 empty] | 70:00 |  |  |  |  | 0:00 | h:mm
| Change Exit Criteria Duration | [9 empty] | 0:00 |  |  |  |  | 0:00 | h:mm
| Change Closure Duration | [9 empty] | 0:00 |  |  |  |  | 0:00 | h:mm
| Total Change Duration | [9 empty] | 420:00 |  |  |  |  | #VALUE! | h:mm
Reviewed by Tower Head
Name:
Date and time :
Reviewed by Implementers
Name:
Team:
Date and time :
Name:
Team:
Date and time :
Name:
Team:
Date and time :
Name:
Team:
Date and time :
Name:
Group Team:
Date and time :
Name:
Team:
Date and time :
Name:
Team:
Date and time :
Note on D2: List the dependant task from the plan. If cell is blank can be done in parallel
Note on E2: If the task applies to a particular Server, or Environment, please specifiy
Note on F2: Area Responsible (i.e. Wintel, Network, Retail Banking, Private Banking etc)
Note on L2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.
Note on Q2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.

## Test DB Names (hidden)
Target Server | Target IP address | Tgt CDB | Tgt PDB
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG1 | SGFRTB01
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG6 | AEFRTB06
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG5 | MYFRTB05
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG4 | HKFRTB04
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG7 | INFRTB07
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG2 | UKFRTB02
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG3 | USFRTB03
HKLPDDPSG001 | 10.23.142.60 | FRTBPS10 | AFFRTB10
HKLPDDPSG001 | 10.23.142.60 | FRTBPSG8 | KRFRTB08
HKLPDDPSG001 | 10.23.142.60 | SAPPRJT1 | SAPPSGL1
HKLPDDPSG001 | 10.23.142.60 | SAPPRJT6 | SAPPSGL6
HKLVDTAPP046 | 10.23.229.50 | SAPPRJT5 | SAPPSGL5
HKLVDTAPP046 | 10.23.229.50 | SAPPRJT4 | SAPPSGL4
HKLPDDPSG001 | 10.23.142.60 | SAPPRJT7 | SAPPSGL7
HKLPDDPSG001 | 10.23.142.60 | SAPPRJT2 | SAPPSGL2
HKLPDDPSG001 | 10.23.142.60 | SAPPRJT3 | SAPPSGL3
HKLPDDPSG001 | 10.23.142.60 | SAPPRJ10 | SAPSGL10
HKLPDDPSG001 | 10.23.142.60 | SAPPRJT8 | SAPPSGL8

## DB Restore
For Restoration to Pre Prod
Instance | Data cut | Source Server | IP address | Src CDB | Src PDB | Target Server | Target Server IP | Tgt CDB | Tgt PDB | Oracle Version
PSFSPRD7 | 4/31/2022 | HKLPDPPSG001 | 10.21.199.11 | POHK7PSF | PSFSPRD7 | HKLVDPAPP050 | 10.23.98.45 | INASPE07 | INASPR07 | 19C
Target Test database (For restoration to UAT)
Source Server | Source IP address | Src CDB | Src PDB | Target Server | Target IP address | Tgt CDB | Tgt PDB | Oracle Version
HKLVDPAPP050 | 10.23.98.45 | INASPE07 | INASPR07 | hklvddapp068 | 10.23.229.85 | INASPE07 | INASPR07 | 19C
Control File details:-
HKLPDPPSG001 | RMAN:control_POHK7PSF_oj0pp8hv_203539_1_1 | 03/31/2022 | 1:23 | PM | 1648704192 | 06/30/2022 | 126 | MB | DC1DBBackupDD12.005 | MEG_CTRL_BKP_DLY_01M_G82 | full
HKLPDPPSG001 | RMAN:control_POHK7PSF_oj0pp8hv_203539_1_1 | 03/31/2022 | 1:23 | PM | 1648704192 | 06/30/2022 | 126 | MB | DC2DBCloneDD12.003 | MEG_CTRL_BKP_DLY_01M_G82 | full
Client | Name | save time |  |  | nsave time | Clone Retention Time |  |  | volume | group | level
HKLPDPPSG001 | RMAN:control_POHK7PSF_0k0psch9_203796_1_1 | 2022-01-04 | 5:50 | PM | 1648806570 | 2022-06-30 | 126 | MB | DC1DBBackupDD12.006 | MEG_CTRL_BKP_DLY_01M_G82 | full
HKLPDPPSG001 | RMAN:control_POHK7PSF_0k0psch9_203796_1_1 | 2022-01-04 | 5:50 | PM | 1648806570 | 2022-06-30 | 126 | MB | DC2DBCloneDD12.003 | MEG_CTRL_BKP_DLY_01M_G82 | full
RFS: TS-48118
CRQ000001542142 | TAS000003584412 | 2022-04-28 13:45 | 2022-04-30 00:30 | hklvdpapp050 | 000000006988047
CRQ000001542142 | TAS000003584412 | 2022-04-28 13:45 | 2022-04-30 00:30 | hklvddapp068 | 000000006988047
Client | Name | save time |  |  | nsave time | Clone Retention Time |  |  | volume | group | level
HKLPDPPSG001 | RMAN:control_POHK7PSF_0k0psch9_203796_1_1 | 2022-01-04 | 5:50 | PM | 1648806570 | 2022-06-30 | 126 | MB | DC1DBBackupDD12.006 | MEG_CTRL_BKP_DLY_01M_G82 | full
HKLPDPPSG001 | RMAN:control_POHK7PSF_0k0psch9_203796_1_1 | 2022-01-04 | 5:50 | PM | 1648806570 | 2022-06-30 | 126 | MB | DC2DBCloneDD12.003 | MEG_CTRL_BKP_DLY_01M_G82 | full

## CRQ Back Out Plan
ATOS High Level - Change Implementation Plan
Task | Task Desription | Host, Server or Envonment name (if applicable) | Task Depndency if applicable | Task Owner | Tower/Domain | Remedy Group | Planned Start Date | Planned Start Time HKT | Planned End Date | Planned End Time HKT | Planned Duration (hour:min) | Actual Start Date | Actual Start Time HKT | Actual End Date | Actual End Time HKT | Actual Duration (hour:min) | Task Implementer (update during CRQ execution) | Comments or Notes
Pre-Back Out Activities *** MANDATORY SECTION
PRE1 | Withdraw e-id for the Servers HKLVDPAPP050 and hklvddapp068 | HKLVDPAPP050; hklvddapp068 | N/A | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
PREX | GO / NO GO CHECKPOINT | N/A | PRE4 | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
Back Out Steps *** MANDATORY SECTION
IMP1 | GO / NO GO CHECKPOINT | N/A | PREX | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00 | [6 empty] | Must be completed before stepping into the change
IMP2 | Remove all the restored DBs , Delete test database restored from Production backup in FS /oradata in pre-prod server and dev server -HKLVDPAPP050 and HKLPDDPSG001 cat drop_db_example.sh export ORACLE_SID=XXXXXXX sqlplus / as sysdba<<EOF set linesize 250 pagesize 10000 time on timing on head on verify on feedback on select instance_name,host_name,name,open_mode from v\$instance,v\$database; select to_char(sysdate,'DD-MON-yyyy hh24:mi:ss')"DATE" from dual; shutdown immediate; startup mount exclusive restrict; select logins,parallel from v\$instance; drop database; | HKLVDPAPP050; HKLPDDPSG001; HKLPDDPSG001 | IMP1 | GBL-OSV-AO-SG MR DBA | Atos | GBL-OSV-AO-SG MR DBA | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
Post Back Out Testing *** MANDATORY SECTION
PIT1 | Ensure all the restored DBs are correctly removed | HKLVDPAPP050; HKLPDDPSG001; HKLPDDPSG001 | IMP2 | SS Team | SCB | SS team | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
PITX | GO / NO GO CHECKPOINT | N/A | PIT1 | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00 | [6 empty] | Must be completed before stepping out of the change
Change Exit Criteria *** MANDATORY SECTION
EXT1 | Alert Review (if blackout initiatied) *
EXT2 | Communicate Completion | N/A | PITX | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
Change Closure *** MANDATORY SECTION
END | Close out Change in Remedy * | N/A | EXT2 | GBL-OSV-AO-HK PROJECT MGMT | Atos | GBL-OSV-AO-HK PROJECT MGMT | 2022-04-28 | 11:00 | 2022-04-29 | 22:00 | 35:00
* | Mandatory Section/Step
Management Data | [9 empty] | Planned | 280:00 | Hour:Minute |  |  | Actual | 0:00 | Hour:Minute
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List the dependant task from the plan. If cell is blank can be done in parallel
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the task applies to a particular Server, or Environment, please specifiy
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Area Responsible (i.e. Wintel, Network, Retail Banking, Private Banking etc)
Note on L2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.
Note on Q2: Automatic calculation in "hh:mm" hour:minute format. Do not overwrite formulas in this column.

## DB restore details (hidden)
For Restoration to Pre Prod
Instance | Data cut | Source Server | IP address | Src CDB | Src PDB | Target Server | Target Server IP | Tgt CDB | Tgt PDB
PSFSPRD1 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK1PSF | PSFSPRD1 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG1 | SGFRTB01
PSFSPRD6 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK6PSF | PSFSPRD6 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG6 | AEFRTB06
PSFSPRD5 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK5PSF | PSFSPRD5 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG5 | MYFRTB05
PSFSPRD4 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK4PSF | PSFSPRD4 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG4 | HKFRTB04
PSFSPRD7 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK7PSF | PSFSPRD7 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG7 | INFRTB07
PSFSPRD2 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK2PSF | PSFSPRD2 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG2 | UKFRTB02
PSFSPRD3 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK3PSF | PSFSPRD3 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG3 | USFRTB03
PSFPRD10 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK10PS | PSFPRD10 | HKLVDPAPP050 | 10.23.98.45 | FRTBPS10 | AFFRTB10
PSFSPRD8 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK8PSF | PSFSPRD8 | HKLVDPAPP050 | 10.23.98.45 | FRTBPSG8 | KRFRTB08
PSFSPRD1 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK1PSF | PSFSPRD1 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT1 | SAPPSGL1
PSFSPRD6 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK6PSF | PSFSPRD6 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT6 | SAPPSGL6
PSFSPRD5 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK5PSF | PSFSPRD5 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT5 | SAPPSGL5
PSFSPRD4 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK4PSF | PSFSPRD4 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT4 | SAPPSGL4
PSFSPRD7 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK7PSF | PSFSPRD7 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT7 | SAPPSGL7
PSFSPRD2 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK2PSF | PSFSPRD2 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT2 | SAPPSGL2
PSFSPRD3 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK3PSF | PSFSPRD3 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT3 | SAPPSGL3
PSFPRD10 | 2020-12-31 | HKLPDPPSG002 | 10.21.199.14 | POHK10PS | PSFPRD10 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJ10 | SAPSGL10
PSFSPRD8 | 2020-12-31 | HKLPDPPSG001 | 10.21.199.11 | POHK8PSF | PSFSPRD8 | HKLVDPAPP050 | 10.23.98.45 | SAPPRJT8 | SAPPSGL8
Target Test database (For restoration to UAT)
Source Server | Source IP address | Src CDB | Src PDB | Target Server | Target IP address | Tgt CDB | Tgt PDB
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG1 | SGFRTB01 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG1 | SGFRTB01
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG6 | AEFRTB06 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG6 | AEFRTB06
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG5 | MYFRTB05 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG5 | MYFRTB05
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG4 | HKFRTB04 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG4 | HKFRTB04
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG7 | INFRTB07 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG7 | INFRTB07
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG2 | UKFRTB02 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG2 | UKFRTB02
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG3 | USFRTB03 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG3 | USFRTB03
HKLVDPAPP050 | 10.23.98.45 | FRTBPS10 | AFFRTB10 | HKLPDDPSG001 | 10.23.142.60 | FRTBPS10 | AFFRTB10
HKLVDPAPP050 | 10.23.98.45 | FRTBPSG6 | KRFRTB08 | HKLPDDPSG001 | 10.23.142.60 | FRTBPSG8 | KRFRTB08
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT1 | SAPPSGL1 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT1 | SAPPSGL1
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT6 | SAPPSGL6 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT6 | SAPPSGL6
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT5 | SAPPSGL5 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT5 | SAPPSGL5
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT4 | SAPPSGL4 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT4 | SAPPSGL4
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT7 | SAPPSGL7 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT7 | SAPPSGL7
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT2 | SAPPSGL2 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT2 | SAPPSGL2
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT3 | SAPPSGL3 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT3 | SAPPSGL3
HKLVDPAPP050 | 10.23.98.45 | SAPPRJ10 | SAPSGL10 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJ10 | SAPSGL10
HKLVDPAPP050 | 10.23.98.45 | SAPPRJT8 | SAPPSGL8 | HKLPDDPSG001 | 10.23.142.60 | SAPPRJT8 | SAPPSGL8
DB Host | DB server IP | DB name (Oracle 11g) | Data Cut
HKLPADGEL01 | 10.20.168.80 | CHNFRTB9 | 2021-01-08

## TNS
DB Name | New

## Prod DB Size
Instance | Size in GB (Approx.)
PSFSPRD7 | 1215
PSFSPRD4 | 839
PSFSPRD7 | 593
PSFSPRD2 | 404
PSFSPRD3 | 210
PSFSPRD8 | 642
PSFSPRD7 | 593
PSFSPRD1 | 1200
PSFSPRD5 | 503

## BO task Details
Blackout Template
All information are mandatory to be filled.
No FQDN in the Server Name column. Only Hostname.
Blackout Date & Time must follow this format: dd/mm/yyyy hh:mm
Blackout Time must follow this format: 24-hours and in HKT time zone.
Blackout will not be performed/extended if less than 30 minutes prior Blackout Start Time/End Time.
Blackout Date & Time must be within the Change Request window.
For Any Change requiring Support From NSM must have a task in Remedy ticket
If ad-hoc requests of Blackout removal is required it must be done with at least 30 minutes of buffer time, provided the Change end time is more than 2 hours away
BO Start Date & time (dd/mm/yyyy hh:mm HKT) | BO End Date & time (dd/mm/yyyy hh:mm HKT) | Server Name | IP Address | Host Type
2020-09-07 13:45 | 2020-09-07 22:00 | Sample | 127.0.0.1 | Windows/Unix

## OAT Approval Form
This tab is only required for changes related RFS
| RFS # |  |  |  |  | Yes
| TCC1 PLATFORM CONTACT |  |  |  |  | No
TCC1 PROJECT MANAGER CONTACT
NO | HOSTNAME | IP ADDRESS | OS PLATFORM | DMZ (YES/NO) | ADDITIONAL APPLICATION MONITORING (if required)
1 | Sample | 127.0.0.1 | Windows/Unix | Yes | for ex, PostgresSQL 12 ,
2 | 0 | 0 | 0 | No
3 | 0 | 0 | 0
4 | 0 | 0 | 0
5 | 0 | 0 | 0
6 | 0 | 0 | 0
7 | 0 | 0 | 0
8 | 0 | 0 | 0
9 | 0 | 0 | 0
10 | 0 | 0 | 0
11 | 0 | 0 | 0
12 | 0 | 0 | 0
13 | 0 | 0 | 0
14 | 0 | 0 | 0
15 | 0 | 0 | 0
16 | 0 | 0 | 0
17 | 0 | 0 | 0
18 | 0 | 0 | 0
19 | 0 | 0 | 0
20 | 0 | 0 | 0
21 | 0 | 0 | 0
22 | 0 | 0 | 0
23 | 0 | 0 | 0
24 | 0 | 0 | 0
25 | 0 | 0 | 0
26 | 0 | 0 | 0
27 | 0 | 0 | 0
28 | 0 | 0 | 0
29 | 0 | 0 | 0
30 | 0 | 0 | 0
31 | 0 | 0 | 0
32 | 0 | 0 | 0
33 | 0 | 0 | 0
34 | 0 | 0 | 0
35 | 0 | 0 | 0

## Associated Docs
EMBED any Associated Documents or Instructions here
Item | Associated to CRQ ImPlan Step | Document

## Postponed@Cancelled
Week | Month | Change Number | Summary | Start Time | End Time | Actual Start Time | Actual End Time | Application Name | Tower | Date/Time Change Turned to IIP Status | Date/Time Change Cancelled / Postponed | Task Implemented | Reason of Postponement/ Cancellation | Next Target Date to be Implemented

## Unsuccessful@Rollback
Week | Month | Change Number | Summary | Start Time | End Time | Actual Start Time | Actual End Time | Application Name | Tower | Date/Time Change Turned to IIP Status | Date/Time Change Unsuccessful /Rollback | Tested in T&D | Incomplete Implementation Plan (Yes/No) Please Elaborate if Yes | Task Implemented | Reason Unsuccessful/Rollback | Next Target Date to be Implemented