## H2 2024 Assign list
Master Change | Child Change | Application | Category | DB Server Name | DR Pair | DR Type | RAC (Yes/No) | OGG Configured (Yes/No) | Validate Servers as part of DR | Planned Switch over Time IST | Planned Switch Back time IST | Implementor | DR Sync Status done (YES/NO) | Check the ASM disk group, file system and tablespace usage not to exceed 80% usage | Check and review each database's alert.log file for any error such as ORA-XXXXX that could potentially prevent the switchover process | DGMGRL configuration | Low Level commands or Runbook for each server (Y/N) | Owner | Escalation | Online/Standby escalation | Customer Confirmation for Switch Over (IST or HKT) | Actual Switch over time in HKT | Actual Switch back time in HKT | Remarks | 1st Round of Sync check | 2st Round of Sync check | Partcipating in DR
|  | BCRS |  | HKLPDPBCR001 | HKLPDSBCR001 |  |  |  |  | 09-09-2024 2:30PM TO 5:30PM IST |  | Narendra | [9 empty] | 21-09-2024 01:30 AM to 02:30 AM
|  | BCRS |  | HKLPDPBCR002 | HKLPDSBCR002 | [6 empty] | Narendra
|  | BCRS |  | HKLPDPBCR003 | HKLPDSBCR003 | [6 empty] | Narendra
|  | CACS |  | HKLVDPAPP096 | HKLVDSAPP096 | [6 empty] | Dinesh/Ajit
|  | CCIB AI Activebot |  | hklvdpapp068 | hklvdsapp068 | [6 empty] | Dinesh/Ajit
|  | CEMS |  | HKLVDPAPP107 | HKLVDSAPP107 | [6 empty] | Dinesh/Ajit
|  | CEMS |  | HKLVDPAPP108 | HKLVDSAPP108 | [6 empty] | Dinesh/Ajit
|  | CEMS |  | HKLVDPAPP109 | HKLVDSAPP109 | [6 empty] | Dinesh/Ajit
|  | CEMS |  | HKLVDPAPP110 | HKLVDSAPP110 | [6 empty] | Dinesh/Ajit
|  | Control-M |  | HKLVDPCTM002 | HKLVDSCTM002 | [6 empty] | Narendra
|  | Control-M |  | HKLVDPCTM003 | HKLVDSCTM003 | [6 empty] | Narendra
|  | Detica-FATCA |  | HKLVDPAPP069 | HKLVDSAPP069 | [6 empty] | Narendra
|  | DLP |  | HKLVDPAPP082 | HKLVDSAPP082 | [6 empty] | Mayuresh
|  | eOPS |  | HKLVDPAPP077 | HKLVDSAPP077 | [6 empty] | Nagaraju
|  | eOPS |  | HKLVDPAPP036 | HKLVDSAPP036 | [6 empty] | Nagaraju
|  | EQTrade |  | HKLVDPAPP035 | HKLVDSAPP035 | [6 empty] | Mayuresh
|  | eSigcap |  | HKLVDPAPP083 | HKLVDSAPP083 | [6 empty] | Ashish/Amarjeet
|  | eSigcap |  | HKLVDPAPP084 | HKLVDSAPP084 | [6 empty] | Ashish/Amarjeet
|  | eSigcap |  | HKLVDPAPP085 | HKLVDSAPP085 | [6 empty] | Ashish/Amarjeet
|  | eSigcap |  | HKLVDPAPP086 | HKLVDSAPP086 | [6 empty] | Ashish/Amarjeet
|  | MICROSTRATEGY |  | HKLVDPAPP103 | HKLVDSAPP103 | [6 empty] | Ashish/Amarjeet
|  | FALCON |  | HKLVDPAPP106 | HKLVDSAPP106 | [6 empty] | Ashish/Amarjeet
|  | FileNet |  | HKLVDPAPP033 | HKLVDSAPP033 | [6 empty] | Ashish/Amarjeet
|  | Finantix |  | HKLPDPFTX001 | HKLPDSFTX001 | [6 empty] | Ashish/Amarjeet
|  | GLEL |  | HKLPAPGEL01 | HKLPASGEL01 | [6 empty] | Ashish/Amarjeet
|  | GPBS |  | HKLVDPAPP116 | HKLVDPAPP116 | [6 empty] | Mayuresh/Datta
|  | GPBS |  | HKLVDPAPP117 | HKLVDPAPP117 | [6 empty] | Mayuresh/Datta
|  | GTE |  | HKLPDPGTE003/004 | HKLPDSGTE003/004 | [6 empty] | Raghu/Amarjeet
|  | HKOE 2.0 |  | HKLPDPOLE003/004 | HKLPDSOLE003/004 | [6 empty] | Nagaraju/Datta
|  | iCDD |  | HKLVDPAPP090 | HKLVDSAPP090 | kanna |  |  |  | 21-09-2024 23:00 to 22-09-2024 01:00 | 22-09-2024 03:00 to 05:00 | Dinesh Dilli
|  | iCDD |  | HKLVDPAPP094 | HKLVDSAPP094 | kanna |  |  |  | 21-09-2024 23:00 to 22-09-2024 01:00 | 22-09-2024 03:00 to 05:00 | Dinesh Dilli
|  | Individual Client Master |  | HKLVDPAPP074 | HKLVDSAPP074 | kanna |  |  |  | 22-09-2024 00:30 to 02:00 | 22-09-2024 05:30 to 07:00 | Dinesh Dilli
|  | Integration Services |  | HKLPIPISI02 | HKLPISISI02 | [6 empty] | Nagaraju/Ajit
|  | Integration Services |  | hklpipisi001a | hklpisisi001b | [6 empty] | Nagaraju/Ajit
|  | INTERNAL_API_GATEWAY |  | HKLPDPEDM01/02/03 | HKLPDSEDM01/02/03 | [6 empty] | Narendra/Benny
|  | Magellan ATP |  | HKLVDPAPP087 | HKLVDSAPP087 | [6 empty] | Raghu/SaiPrasad
|  | Magellan DTP |  | HKLVDPAPP100 | HKLVDSAPP100 | [6 empty] | Raghu/SaiPrasad
|  | MAGELLAN OTP |  | HKLPDPOTP003/004 | HKLPDSOTP003/004 | [6 empty] | Raghu/SaiPrasad
|  | Magellan OTP |  | HKLPDPOTP005 | HKLPDSOTP005 | [6 empty] | Raghu/SaiPrasad
|  | Magellan RTP |  | HKLVDPAPP101 | HKLVDSAPP101 | [6 empty] | Raghu/SaiPrasad
|  | Magellan RTP |  | HKLVDPAPP102 | HKLVDSAPP102 | [6 empty] | Raghu/SaiPrasad
|  | Mantas-AML |  | HKLPDPMTC01/02/03 | HKLPDSMTC01/02/03 | [6 empty] | lalit/Mrunalini/Amarjeet/Vipul
|  | Mantas-AML |  | HKLPDPMTC005/006/007 | HKLPDSMTC005/006/007 | [6 empty] | lalit/Mrunalini/Amarjeet/Vipul
|  | MDIS |  | HKLPDPMDS01 | HKLPDSMDS01 | [6 empty] | lalit/Mrunalini/Amarjeet/Vipul
|  | Online FX |  | HKLPDPOFX001/002 | HKLPDSOFX001/002 | [6 empty] | lalit/Mrunalini/Amarjeet/Vipul
|  | PEOPLESOFT FTP |  | PG1146 | RG1146 | [6 empty] | Raghu/Amarjeet
|  | PEOPLESOFT FTP |  | PG1147 | RG1147 | [6 empty] | Raghu/Amarjeet
|  | PEOPLESOFT GL |  | HKLPDPPSG001 | HKLPDSPSG001 | [6 empty] | Dinesh/Ajit/Vipul
|  | PEOPLESOFT GL |  | HKLPDPPSG002 | HKLPDSPSG002 | [6 empty] | Dinesh/Ajit/Vipul
|  | PERFORMANCE MI |  | PG1198 | RG1198 | [6 empty] | Lalit/Vipul/Rakesh
|  | Rapid Cash Plus |  | HKLVDSAPP058 | HKLVDSAPP058 | [6 empty] | Datta/Benny
Decom |  | RAyCo |  | HKLPDPRAT001 | HKLPDSRAT001 | [6 empty] | Dinesh Dilli/Benny
|  | RAyCo |  | HKLPDPRAC002 | HKLPDSRAC002 | Sundararaj, Vellachamy <Vellaichamy.Sundararaj@sc.com> |  |  |  | 21-09-2024 22:30 to 23:30 | 22-09-2024 05:00 to 06:00 | Dinesh Dilli/Benny
|  | Rayco - Rubik |  | HKLPDPRAC001 | HKLPDSRAC001 | Sundararaj, Vellachamy <Vellaichamy.Sundararaj@sc.com> |  |  |  | 21-09-2024 22:30 to 23:30 | 22-09-2024 05:00 to 06:00 | Dinesh Dilli/Benny
|  | RCMS |  | HKLVDPAPP091 | HKLVDSAPP091 | [6 empty] | Benny/Dinesh/Vipul
|  | RCMS |  | HKLVDPAPP092 | HKLVDSAPP092 | [6 empty] | Benny/Dinesh/Vipul
|  | RPPBC |  | HKLPDPPTC001 | HKLPDSPTC001 | [6 empty] | Ashish/Amarjeet
|  | RTAS |  | HKLVDPAPP051 | HKLVDSAPP051 | [6 empty] | Narendra/Rakesh/Vipul
|  | SCPAY |  | HKLPDPNPP001/002 | HKLPDSNPP001/002 | [6 empty] | Ajit/Vipul/Benny
|  | Seccure |  | HKLPDPSEC001/002/003 | HKLPDSSEC001/002/003 | [6 empty] | Ajit/Vipul/Benny
|  | STS |  | HKLPDPSTS01/02 | HKLPDSSTS01/02 |  |  |  |  | 22-09-2024 02:00 - 02:30 | 22-09-2024 07:30 - 08:00 | Lalit/Dinesh Dill/Rakesh
|  | STS |  | HKLPDPSTS03 | HKLPDSSTS03 |  |  |  |  | 22-09-2024 02:00 - 02:30 | 22-09-2024 07:30 - 08:00 | Lalit/Dinesh Dill/Rakesh
|  | TradePort COCOA |  | PG189 | RG189 |  |  |  |  | 22-09-2024 01:30 to 02:25 | 22-09-2024 04:10 to 04:55 | Dinesh Dilli/Benny
|  | TradePort COCOA |  | PG190 | RG190 |  |  |  |  | 22-09-2024 01:30 to 02:25 | 22-09-2024 04:10 to 04:55 | Dinesh Dilli/Benny
|  | Triple_A_Plus |  | HKLPDPTAP01/02/03 | HKLPDSTAP01/02/03 | [6 empty] | Narendra/Rakesh/Vipul
|  | UTS |  | HKLVDPAPP089 | HKLVDSAPP089 | [6 empty] | Nagaraju/Vipul
|  | Wealth FX SG |  | HKLPDPWEB001/002 | HKLPDSWEB001/002 | [6 empty] | Nagaraju/Datta
Workbench
|  | FinRep |  | HKLVDPAPP118 | HKLVDSAPP118
|  | IFRS |  | HKLVDPAPP119 | HKLVDSAPP119

## Sheet1
"Stop/failover Application Services from PG189 -> RG189 and PG190 -> RG190 1. Stop Golden Gate - on PG189/PG190. Oracle replication services running on PG189 using the operator panel.- Will be done by DBA team 2. Stop Oracle services in PG189 & PG190 #hagrp -offline CocodbCluster -sys pg189 and #hagrp -offline CocorptCluster -sys pg190 # hastatus -sum (confirm CocodbCluster & CocorptCluster is OFFLINE in PG189 & PG190) – Will be done by AIX team 3. Split the TC on PG/RG189 and PG/RG190 (TC Split, P-Vol: Mega, S-Vol: Jumbo), – Will be done by AIX team. If VCS not working, then perform this task manually 4. Start Oracle service on RG189 # hagrp -online CocodbCluster -sys rg189 #hastatus –sum (confirm CocodbCluster is ONLINE in RG189) – Will be done by AIX team 5. Start Oracle service on RG190 # hagrp -online CocorptCluster -sys rg190 #hastatus –sum (confirm CocorptCluster is ONLINE in RG190) – Will be done by AIX team 6. Start Golden Gate on RG189 and RG190. - Will be done by DBA team" | "Stop/failover Application Services from RG189-> PG189 and RG190-> PG190. Execute the following step from RG189 and RG190 : 1. Stop Golden Gate in RG189 and RG190. - Will be done by DBA team 2. Stop Oracle services in RG189 #hagrp -offline CocodbCluster -sys rg189 #hastatus –sum (confirm CocodbCluster is OFFLINE on RG189) – Will be done by AIX team 3. Stop Oracle services in RG190 #hagrp -offline CocorptCluster -sys rg190 #hastatus –sum (confirm CocorptCluster is OFFLINE on RG190) – Will be done by AIX team Execute the following step from PG189 and PG190 : 4. Start Oracle services in PG189 #hagrp -online CocodbCluster -sys pg189 #hastatus –sum (confirm CocodbCluster is ONLINE in PG189) – Will be done by AIX team 5. Start Oracle services in PG190 #hagrp -online CocorptCluster -sys pg190 #hastatus –sum (confirm CocorptCluster is ONLINE in PG190) – Will be done by AIX team 6. Start Golden Gate on PG189 and PG190. - Oracle replication services using operator Panel in PG189. - Will be done by DBA team"