## Sheet1
DR Activities | [11 empty] | Standard DR Drill Flow (For Reference)
Instructions:
1. Please refer to the worksheet "Activities (Example)" to fill in below activities plan. | [7 empty] | Version: | 4.17
2. Please read the comment in each specified cell in the "Activities (Example)" worksheet before you input corresponding necessary info. | [7 empty] | Date: | 2024-09-22
[8 empty] | Updated By: | Arthur
3. Please note that all the date(DD/MMM/YY) and time(hh:mm)(24-hrs) in Column G, H, I are in 24 hrs format, HKT, time in column J, K are in IST and derived from column H and I. | [7 empty] | Status: | Completed
4. Please note only those tasks which marked "Y" in Column E "Real DR" will be counted towards RTO/ SLA.
5. Please be reminded to state the server name for all activities.
6. Please indicate high risk activity (All SAN Truecopy / NAS operation) in Column L.
7. Please highlight which tasks are automated by using Rundeck.
8. Please highlight verification and sign off activities.
9. Please insert additional rows if necessary.
10. Please note that END should be marked at the bottom line of the DR activities plan.
11. Depends on your input, some fields may not required and it will be filled in grey colour.
12. Please provide the job handling details (job name, order date, handling details (Hold/release/Skip/re-run) in Control-M Jobs page if any job handling is required to be performed by Atos EOC.
13.Please ensure the mandatory stages and standard flows in the right are included and followed.
14. Please state clearly about verifications to avoid confusion:
- Technical Support Verification – Technical Support verification test
- User Verification Test (UVT) – User strictly means “Business User”
Appl | Country | Task ID | Dependency | Real DR | DR Drill | DR Drill Date | DR Drill | DR Drill | DR Drill | DR Drill | High Risk Activity | Activity | Resp by / Involved Parties | Action after Task | Status | Preliminary Checking
[7 empty] | Start Time (HKT) | End Time (HKT) | Start Time (IST) | End Time (IST)
RAyCo BA | Global | 1 | NA | N | Y | 2024-09-22 | 0:00 | 0:30 | 21:30 | 22:00 | N | Update start up type to Task service as mentioned in "AIG to change Startup type.docx" | RAYCO PROD TSO SUP |  |  | Completed
RAyCo BA | Global | 2 | NA | N | Y | 2024-09-22 | 0:00 | 0:30 | 21:30 | 22:00 | N | PSS to check batch complete and hold the batch | RAYCO PROD TSO SUP | PSS give the confirmation in DR channel RAyCo is ready to start DR, and update status to DR coordinator. |  | Completed
RAyCo BA | Global | 3 | 2 | Y | Y | 2024-09-22 | 0:30 | 1:00 | 22:00 | 22:30 | N | PSS to stop task service and spark services | RAYCO PROD TSO SUP |  |  | Completed
HKWPAPRAT001
SCB_SparkMaster714
SCB_SparkWorker714
SCB_RiskConfidence714
HKWPAPRAC001
TS_RCO_GBL_PROD_RCO71419c_1 --> TS_RCO_GBL_PROD_RCO71419c_120
HKWPAPRAT002 / HKWVAPAPP670 / HKWVAPAPP671 / HKWVAPAPP672 / HKWVAPAPP690 / HKWVAPAPP693
SCB_SparkMaster72
SCB_SparkWorker72
SCB_RiskConfidence72
TS_RCO72_IRRBB_PROD_RCO72_PH_1 --> TS_RCO72_IRRBB_PROD_RCO72_PH_24
TS_RCO72_IRRBB_PROD_RCO72_VM1_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM1_8
TS_RCO72_IRRBB_PROD_RCO72_VM2_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM2_8
TS_RCO72_IRRBB_PROD_RCO72_VM3_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM3_8
TS_RCO72_IRRBB_PROD_RCO72_VM4_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM4_8
TS_RCO72_IRRBB_PROD_RCO72_VM5_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM5_8
RAyCo BA | Global | 4 | 2 | Y | Y | 2024-09-22 | 0:30 | 1:00 | 22:00 | 22:30 | N | Datastage Failover HKLPAPRAT001 | RAYCO PROD TSO SUP | PSS inform DBA to prepare the switch over of Database as task#5, and infrom LINUX to prepare bring down VIP and unmount SAN FS as per task#6. |  | Completed
[12 empty] | -------------------------------- | INFRA SERVER - UNIX - ATOS PROD TSO SUP
PSS stop DataStage services under HKLPAPRAT001 via using RunDeck.
Appendix:
DataStage Services shutdown by root procedure, if any issue PSS can't shutdown via RunDeck, need Unix help:
1) Login as root
2) cd `cat /.dshome` and execute the below command.
3) . ./dsenv
4) bin/uv -admin -stop
5) netstat -an ¦ grep 31538 ¦ wc -l (wait till output should be display "0")
6) /IBM/InformationServer/ASBNode/bin/NodeAgents.sh stop
7) /IBM/InformationServer/ASBServer/bin/MetadataServer.sh stop
8) /IBM/InformationServer/shared-open-source/bin/stop-linux-services.sh
9) su - db2inst1 and then run db2stop
[If we get any issues while executing 9th step, then Linux team has to reboot the server and try the steps]
RAyCo BA | Global | 5 | 4 | Y | Y | 2024-09-22 | 1:00 | 2:00 | 22:30 | 23:30 | N | DBA switch over DB instance POHK1RCO from HKLPDPRAC002 to HKLPDSRAC002 | AO-IN MR DBA TSO SUP | DBA confrim the POHK1RCO / POHK1RAC are swichover to DR node |  | Completed
DBA switch over DB instance POHK1RAC from HKLPDPRAC001 to HKLPDSRAC001
RAyCo BA | Global | 6 | 4 | Y | Y | 2024-09-22 | 1:00 | 2:00 | 22:30 | 23:30 | N | 1. Linux stop Control-M Agent, bring down VIP and unmount below SAN FS mountpoints from HKLPAPRAT001 | INFRA SERVER - UNIX - ATOS PROD TSO SUP | Linux confirm the unmount actions complete and send mail to DR coordinator and PSS complete of task#6 |  | Completed
umount /dstemp
umount /dshome
umount /dsprojects
umount /IBM/db2
umount /IBM/WebSphere
umount /IBM/InformationServer
umount /backup
umount /resource1
umount /resource2
umount /resource3
umount /scratch1
umount /scratch2
umount /scratch3
umount /ASPIRE
umount /apps
umount /usr/controlm
vgchange -an HKLPAPRAT001_DSVG
2. Proceed update HORCM from HKLPAPRAT001 to HKLPASRAT001
TC Direction is MEGA -> JUMBO
RAyCo BA | Global | 7 | 6 | Y | Y | 2024-09-22 | 2:00 | 2:00 | 23:30 | 23:30 | N | PSS provide confirmation in VM – P2V SRM conference bridge for the failover of HKLVAPAPP720 / HKLVAPAPQ996 from Mega to Jumbo. | RAYCO PROD TSO SUP | PSS inform VM SRM to execute SRM failover. |  | Completed
RAyCo BA | Global | 8 | 7 | Y | Y | 2024-09-22 | 2:00 | 3:00 | 23:30 | 0:30 | N | Perform SRM failover - HKLVAPAPP720 to HKLVASAPP720 | ALL-GBL-TS-PSRV-VIRTATOS-PRJ | SRM confirm the SRM failover complete and send mail to DR coordinator and PSS complete of task#8 |  | Completed
Perform SRM failover - HKLVAPAPQ996 to HKLVASAPQ996
RAyCo BA | Global | 9 | 6 | Y | Y | 2024-09-22 | 2:00 | 2:00 | 23:30 | 23:30 | N | PSS provide confirmation in DR command centre conference bridge/ Groupchat for the failover of Metro Cluster NAS from Mega to Jumbo. | RAYCO PROD TSO SUP | PSS inform Storage to execute NAS failover. |  | Completed
RAyCo BA | Global | 10 | 9 | Y | Y | 2024-09-22 | 2:00 | 3:00 | 23:30 | 0:30 | N | Failover of Metro Cluster NAS from Mega to Jumbo. | GBL-OSV-AO-HK MR STORAGE | STORAGE confirm the NAS failover complete and send mail to DR coordinator and PSS complete of task#10 |  | Completed
RAyCo BA | Global | 11 | 10 | Y | Y | 2024-09-22 | 3:00 | 4:00 | 0:30 | 1:30 | N | 1. Linux check TC direction and make sure P-VOL at HKLPASRAT001. Mount below SAN FS mountpoints in HKLPASRAT001 | INFRA SERVER - UNIX - ATOS PROD TSO SUP | Linux confirm the mount actions complete and send mail to DR coordinator and PSS complete of task#11 |  | Completed
vgchange -ay HKLPAPRAT001_DSVG
mount /dev/mapper/HKLPAPRAT001_DSVG-ASPIRE_lv /ASPIRE
mount /dev/mapper/HKLPAPRAT001_DSVG-IBMInformationServer_lv /IBM/InformationServer
mount /dev/mapper/HKLPAPRAT001_DSVG-scratch3_lv /scratch3
mount /dev/mapper/HKLPAPRAT001_DSVG-IBMdb2_lv /IBM/db2
mount /dev/mapper/HKLPAPRAT001_DSVG-resource2_lv /resource2
mount /dev/mapper/HKLPAPRAT001_DSVG-usrcontrolm_lv /usr/controlm
mount /dev/mapper/HKLPAPRAT001_DSVG-backup_lv /backup
mount /dev/mapper/HKLPAPRAT001_DSVG-scratch1_lv /scratch1
mount /dev/mapper/HKLPAPRAT001_DSVG-scratch2_lv /scratch2
mount /dev/mapper/HKLPAPRAT001_DSVG-dshome_lv /dshome
mount /dev/mapper/HKLPAPRAT001_DSVG-resource3_lv /resource3
mount /dev/mapper/HKLPAPRAT001_DSVG-dstemp_lv /dstemp
mount /dev/mapper/HKLPAPRAT001_DSVG-apps_lv /apps
mount /dev/mapper/HKLPAPRAT001_DSVG-dsprojects_lv /dsprojects
mount /dev/mapper/HKLPAPRAT001_DSVG-resource1_lv /resource1
mount /dev/mapper/HKLPAPRAT001_DSVG-IBMWebSphere_lv /IBM/WebSphere
2. Linux bring up VIP first and then start up Control-M Agent
RAyCo BA | Global | 12 | 11 | Y | Y | 2024-09-22 | 4:00 | 5:00 | 1:30 | 2:30 | N | PSS start DataStage services under HKLPASRAT001 via using RunDeck. | RAYCO PROD TSO SUP |  |  | Completed
INFRA SERVER - UNIX - ATOS PROD TSO SUP
Appendix:
DataStage Services startup by root procedure, if any issue PSS can't startup via RunDeck, need Unix help:
1) Login as root
2) su - db2inst1 and then db2start
3) /IBM/InformationServer/shared-open-source/bin/start-linux-services.sh
4) /IBM/InformationServer/ASBServer/bin/MetadataServer.sh run
5) /IBM/InformationServer/ASBNode/bin/NodeAgents.sh start
6) cd `cat /.dshome` and execute the below commands.
7) . ./dsenv
8) bin/uv -admin -start
9) ps -ef ¦ grep dsrpcd & netstat -an ¦ grep 31538
RAyCo BA | Global | 13 | 11 | Y | Y | 2024-09-22 | 4:00 | 5:00 | 1:30 | 2:30 | N | PSS to start task service and spark services | RAYCO PROD TSO SUP |  |  | Completed
HKWPASRAT001
SCB_SparkMaster714
SCB_SparkWorker714
SCB_RiskConfidence714
HKWPASRAC001
TS_RCO_GBL_PROD_19CRCO714_1 --> TS_RCO_GBL_PROD_19CRCO714_120
HKWPASRAT002 / HKWVASAPP670 / HKWVASAPP671 / HKWVASAPP672 / HKWVASAPP690 / HKWVASAPP693
SCB_SparkMaster72
SCB_SparkWorker72
SCB_RiskConfidence72
TS_RCO72_IRRBB_PROD_RCO72_PH_1 --> TS_RCO72_IRRBB_PROD_RCO72_PH_24
TS_RCO72_IRRBB_PROD_RCO72_VM1_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM1_8
TS_RCO72_IRRBB_PROD_RCO72_VM2_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM2_8
TS_RCO72_IRRBB_PROD_RCO72_VM3_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM3_8
TS_RCO72_IRRBB_PROD_RCO72_VM4_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM4_8
TS_RCO72_IRRBB_PROD_RCO72_VM5_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM5_8
RAyCo BA | Global | 14 | 11 | Y | Y | 2024-09-22 | 4:00 | 5:00 | 1:30 | 2:30 | N | HKLVASAPP719 / HKLVASAPP919 | RAYCO PROD TSO SUP |  |  | Completed
START and Verify HTTPD/JBoss services via RunDeck
RAyCo BA | Global | 15 | 14 | Y | Y | 2024-09-22 | 5:00 | 7:00 | 2:30 | 4:30 | N | PSS execute cut-run for RAyCo | RAYCO PROD TSO SUP | PSS confirm failover success and provide sign-off in sharepoint and send mail to DR coordinator |  | Completed
RAyCo BA | Global | 16 | 15 | Y | Y | 2024-09-22 | 7:00 | 7:00 | 4:30 | 4:30 | N | PSS confirm the UVT and faillover back to orignial node and Retest | RAYCO PROD TSO SUP |  |  | Completed
RAyCo BA | Global | 17 | 16 | Y | Y | 2024-09-22 | 7:00 | 7:30 | 4:30 | 5:00 | N | PSS to stop task service and spark services | RAYCO PROD TSO SUP |  |  | Completed
HKWPASRAT001
SCB_SparkMaster714
SCB_SparkWorker714
SCB_RiskConfidence714
HKWPASRAC001
TS_RCO_GBL_PROD_19CRCO714_1 --> TS_RCO_GBL_PROD_19CRCO714_120
HKWPASRAT002 / HKWVASAPP670 / HKWVASAPP671 / HKWVASAPP672 / HKWVASAPP690 / HKWVASAPP693
SCB_SparkMaster72
SCB_SparkWorker72
SCB_RiskConfidence72
TS_RCO72_IRRBB_PROD_RCO72_PH_1 --> TS_RCO72_IRRBB_PROD_RCO72_PH_24
TS_RCO72_IRRBB_PROD_RCO72_VM1_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM1_8
TS_RCO72_IRRBB_PROD_RCO72_VM2_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM2_8
TS_RCO72_IRRBB_PROD_RCO72_VM3_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM3_8
TS_RCO72_IRRBB_PROD_RCO72_VM4_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM4_8
TS_RCO72_IRRBB_PROD_RCO72_VM5_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM5_8
RAyCo BA | Global | 18 | 16 | Y | Y | 2024-09-22 | 7:00 | 7:30 | 4:30 | 5:00 | N | Datastage Failback HKLPASRAT001 | RAYCO PROD TSO SUP | PSS inform DBA to prepare the switch back of Database as task#19, and infrom LINUX to prepare bring down VIP and unmount SAN FS as per task#20. |  | Completed
[12 empty] | -------------------------------- | INFRA SERVER - UNIX - ATOS PROD TSO SUP
PSS stop DataStage services under HKLPASRAT001 via using RunDeck.
Appendix:
DataStage Services shutdown by root procedure, if any issue PSS can't shutdown via RunDeck, need Unix help:
1) Login as root
2) cd `cat /.dshome` and execute the below command.
3) . ./dsenv
4) bin/uv -admin -stop
5) netstat -an ¦ grep 31538 ¦ wc -l (wait till output should be display "0")
6) /IBM/InformationServer/ASBNode/bin/NodeAgents.sh stop
7) /IBM/InformationServer/ASBServer/bin/MetadataServer.sh stop
8) /IBM/InformationServer/shared-open-source/bin/stop-linux-services.sh
9) su - db2inst1 and then run db2stop
[If we get any issues while executing 9th step, then Linux team has to reboot the server and try the steps]
RAyCo BA | Global | 19 | 18 | Y | Y | 2024-09-22 | 7:30 | 8:30 | 5:00 | 6:00 | N | DBA switch back DB instance POHK1RCO from HKLPDSRAC002 to HKLPDPRAC002 | AO-IN MR DBA TSO SUP | DBA confrim the POHK1RCO / POHK1RAC are swichback to PROD node |  | Completed
DBA switch back DB instance POHK1RAC from HKLPDSRAC001 to HKLPDPRAC001
RAyCo BA | Global | 20 | 18 | Y | Y | 2024-09-22 | 7:30 | 8:30 | 5:00 | 6:00 | N | 1. Linux stop Control-M Agent, bring down VIP and unmount below SAN FS mountpoints from HKLPASRAT001 | INFRA SERVER - UNIX - ATOS PROD TSO SUP | Linux confirm the unmount actions complete and send mail to DR coordinator and PSS complete of task#20 |  | Completed
umount /dstemp
umount /dshome
umount /dsprojects
umount /IBM/db2
umount /IBM/WebSphere
umount /IBM/InformationServer
umount /backup
umount /resource1
umount /resource2
umount /resource3
umount /scratch1
umount /scratch2
umount /scratch3
umount /ASPIRE
umount /apps
umount /usr/controlm
vgchange -an HKLPASRAT001_DSVG
2. Proceed update HORCM from HKLPASRAT001 to HKLPAPRAT001
TC Direction is JUMBO -> MEGA
RAyCo BA | Global | 21 | 20 | Y | Y | 2024-09-22 | 8:30 | 8:30 | 6:00 | 6:00 | N | PSS provide confirmation in VM – P2V SRM conference bridge for the failback of HKLVAPAPP720 / HKLVAPAPQ996 from Jumbo to Mega. | RAYCO PROD TSO SUP | PSS inform VM SRM to execute SRM failback. |  | Completed
RAyCo BA | Global | 22 | 21 | Y | Y | 2024-09-22 | 8:30 | 9:30 | 6:00 | 7:00 | N | Perform SRM failback - HKLVASAPP720 to HKLVAPAPP720 | ALL-GBL-TS-PSRV-VIRTATOS-PRJ | SRM confirm the SRM failback complete and send mail to DR coordinator and PSS complete of task#22 |  | Completed
Perform SRM failover - HKLVASAPQ996 to HKLVAPAPQ996
RAyCo BA | Global | 23 | 20 | Y | Y | 2024-09-22 | 8:30 | 8:30 | 6:00 | 6:00 | N | PSS provide confirmation in DR command centre conference bridge/ Groupchat for the fallback of Metro Cluster NAS rom Jumbo to Mega. | RAYCO PROD TSO SUP | PSS inform Storage to execute NAS failback. |  | Completed
RAyCo BA | Global | 24 | 23 | Y | Y | 2024-09-22 | 8:30 | 9:30 | 6:00 | 7:00 | N | Failback of Metro Cluster NAS from Jumbo to Mega. | GBL-OSV-AO-HK MR STORAGE | STORAGE confirm the NAS failback complete and send mail to DR coordinator and PSS complete of task#24 |  | Completed
RAyCo BA | Global | 25 | 24 | Y | Y | 2024-09-22 | 9:30 | 10:30 | 7:00 | 8:00 | N | 1. Linux check TC direction and make sure P-VOL at HKLPAPRAT001. Mount below SAN FS mountpoints in HKLPAPRAT001 | INFRA SERVER - UNIX - ATOS PROD TSO SUP | Linux confirm the mount actions complete and send mail to DR coordinator and PSS complete of task#25 |  | Completed
vgchange -ay HKLPAPRAT001_DSVG
mount /dev/mapper/HKLPAPRAT001_DSVG-ASPIRE_lv /ASPIRE
mount /dev/mapper/HKLPAPRAT001_DSVG-IBMInformationServer_lv /IBM/InformationServer
mount /dev/mapper/HKLPAPRAT001_DSVG-scratch3_lv /scratch3
mount /dev/mapper/HKLPAPRAT001_DSVG-IBMdb2_lv /IBM/db2
mount /dev/mapper/HKLPAPRAT001_DSVG-resource2_lv /resource2
mount /dev/mapper/HKLPAPRAT001_DSVG-usrcontrolm_lv /usr/controlm
mount /dev/mapper/HKLPAPRAT001_DSVG-backup_lv /backup
mount /dev/mapper/HKLPAPRAT001_DSVG-scratch1_lv /scratch1
mount /dev/mapper/HKLPAPRAT001_DSVG-scratch2_lv /scratch2
mount /dev/mapper/HKLPAPRAT001_DSVG-dshome_lv /dshome
mount /dev/mapper/HKLPAPRAT001_DSVG-resource3_lv /resource3
mount /dev/mapper/HKLPAPRAT001_DSVG-dstemp_lv /dstemp
mount /dev/mapper/HKLPAPRAT001_DSVG-apps_lv /apps
mount /dev/mapper/HKLPAPRAT001_DSVG-dsprojects_lv /dsprojects
mount /dev/mapper/HKLPAPRAT001_DSVG-resource1_lv /resource1
mount /dev/mapper/HKLPAPRAT001_DSVG-IBMWebSphere_lv /IBM/WebSphere
2. Linux bring up VIP first and then start up Control-M Agent
RAyCo BA | Global | 26 | 25 | Y | Y | 2024-09-22 | 10:30 | 11:30 | 8:00 | 9:00 | N | PSS start DataStage services under HKLPASRAT001 via using RunDeck. | RAYCO PROD TSO SUP |  |  | Completed
INFRA SERVER - UNIX - ATOS PROD TSO SUP
Appendix:
DataStage Services startup by root procedure, if any issue PSS can't startup via RunDeck, need Unix help:
1) Login as root
2) su - db2inst1 and then db2start
3) /IBM/InformationServer/shared-open-source/bin/start-linux-services.sh
4) /IBM/InformationServer/ASBServer/bin/MetadataServer.sh run
5) /IBM/InformationServer/ASBNode/bin/NodeAgents.sh start
6) cd `cat /.dshome` and execute the below commands.
7) . ./dsenv
8) bin/uv -admin -start
9) ps -ef ¦ grep dsrpcd & netstat -an ¦ grep 31538
RAyCo BA | Global | 27 | 25 | Y | Y | 2024-09-22 | 10:30 | 11:30 | 8:00 | 9:00 | N | PSS to start task service and spark services | RAYCO PROD TSO SUP |  |  | Completed
HKWPAPRAT001
SCB_SparkMaster714
SCB_SparkWorker714
SCB_RiskConfidence714
HKWPAPRAC001
TS_RCO_GBL_PROD_RCO71419c_1 --> TS_RCO_GBL_PROD_RCO71419c_120
HKWPAPRAT002 / HKWVAPAPP670 / HKWVAPAPP671 / HKWVAPAPP672 / HKWVAPAPP690 / HKWVAPAPP693
SCB_SparkMaster72
SCB_SparkWorker72
SCB_RiskConfidence72
TS_RCO72_IRRBB_PROD_RCO72_PH_1 --> TS_RCO72_IRRBB_PROD_RCO72_PH_24
TS_RCO72_IRRBB_PROD_RCO72_VM1_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM1_8
TS_RCO72_IRRBB_PROD_RCO72_VM2_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM2_8
TS_RCO72_IRRBB_PROD_RCO72_VM3_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM3_8
TS_RCO72_IRRBB_PROD_RCO72_VM4_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM4_8
TS_RCO72_IRRBB_PROD_RCO72_VM5_1 --> TS_RCO72_IRRBB_PROD_RCO72_VM5_8
RAyCo BA | Global | 28 | 25 | Y | Y | 2024-09-22 | 10:30 | 11:30 | 8:00 | 9:00 | N | HKLVAPAPP719 / HKLVAPAPP919 | RAYCO PROD TSO SUP |  |  | Completed
START and Verify HTTPD/JBoss services via RunDeck
RAyCo BA | Global | 29 | 27 | Y | Y | 2024-09-22 | 11:30 | 13:30 | 9:00 | 11:00 | N | PSS execute cut-run for RAyCo | RAYCO PROD TSO SUP |  |  | Completed
RAyCo BA | Global | 30 | 28 | Y | Y | 2024-09-22 | 13:30 | 14:00 | 11:00 | 11:30 | N | PSS resume batch and monitor | RAYCO PROD TSO SUP | PSS confirm failback success and provide sign-off in sharepoint and send mail to DR coordinator |  | Completed
RAyCo BA | Global | 31 | 29 | Y | Y | 2024-09-22 | 14:00 | 14:30 | 11:30 | 12:00 | N | NSM team upload the Latest ASRM to ATOS invetory. | GDTS TOOLING - HK MR NSM TSO SUP | NSM update ASRM to ATOs inventory |  | Completed
END